## Cover page
PROGRESS REPORT NO 2
Title of the Project: | Sustainable and effective use of cultural and historical heritage for development of tourism in Daugavpils, Kupiskis, Orsha
Project index No: |  | ENI-LLB-1-001
Name of the Lead Beneficiary: |  | Daugavpils Municipality Culture and History Museum
Name, position and contact details of the Lead Beneficiary’s authorised person: |  | Name, Surname, Director, e-mail: name.surname@daugavpils.lv, phone: +371 XXXXXXXX
Reporting period: | from | 02/05/2019 | to | 01/11/2019
Website(s) of the Beneficiaries where information on the Project is available |  | https://www.daugavpils.lv/go.php/lv/projekti www.orsha-muzej.by/projects http://www.kupiskis.lt/apie-mus/projektai
• This Progress Report must be completed and signed by the Lead Beneficiary’s signatory of the Declaration by the Applicant in the Grant Application Form or other authorised representative of the Lead Beneficiary.
• The Progress Report must be submitted in a bound 1 original and 1 copy, certified as true, in paper version and in electronic version.
• The Progress Report must be sent to the Joint Technical Secretariat to the following address:
Joint Technical Secretariat Konstitucijos pr. 7, LT-09308, Vilnius, Lithuania
• The Joint Technical Secretariat/ Managing Authority will reject any incomplete or badly completed reports.
• The answers to all questions must cover the respective reporting period.
• Add Letters of endorsement issued by Beneficiaries proving they have read the Progress Report and they comply with the provided information. Each Beneficiary shall sign a separate letter, indicating the date of signature of the Progress Report they refer to.
• For ecological reasons we suggest to use double-sided printouts as much as possible.
Please provide the direct links to the web-pages, sections, where the information about the project is available.
In 1 original (some documents are allowed as copies) and 1 e-version. For the rules of submission see Guidelines for Grant Applicants, section 3.5.2.
The reporting period is taken from the Reporting Schedule.
IMPORTANT: having printed out the report, before submission, please make sure that all sections are printed correctly, no text disappeared or became invisible.

## Reporting period
1. IMPLEMENTATION OF ACTIVITIES PER REPORTING PERIOD
1. If there is no information to be indicated, mark the relevant text fields with N/A.
2. If additional information is to be indicated, add as many rows as necessary.
1.1 The first group of activities (GA1)
Planned activities | Activities implemented within the reporting period | Outputs produced within the current reporting period Outputs are immediate products of the project activities: tangible goods, services and infrastructure that activities produce |  | Outputs planned for the next reporting period Planned outputs for next 6-months reporting period, NOT all remaining outputs until the end of the project
| Describe briefly the activity implemented within the reporting period (what was done, by whom, where, when and how it was implemented). Indicate the involved beneficiaries and participants. In case of events (work group / steering committee meetings) also indicate general issues/topics discussed and main decisions, if applicable. * When reporting GA1 activities, use the style and language as in the Project Description. * Do not mention names, surnames of persons involved in the project activities. * Indicate how the project managing bodies were formed, give information of orders on appointment of Work Group, Steering Committee members.. | Description of related outputs | Number of outputs | Description of related outputs | Number of outputs
|  | * Outputs shall be taken from respective sections of the Project Description. Please strictly use outputs how they are indicated in the Project Description. * Indicate here only the achieved outputs during the reporting period | * Indicate the full number of outputs produced, not a fraction (e.g., not 0,5 if 1 is planned) | * Indicate only those outputs, which are planned to be achieved in full within next 6-months reporting period, NOT partly or planned just to be started. * Planned outputs shall correspond to the Project Description. | * Indicate full number of outputs to be produced, not a fraction (e.g., not 0,5 if 1 is planned)
Activity 1.1 Management and coordination system | Example. The project management bodies were formed by the project Beneficiaries, orders of staff appointment for the project implementation are issued by the Beneficiaries' organisations. 4 project staff as project manager, project manager assistant, financial manager and information specialist appointed by LB order No. SR-23 of 2019-04-06 (Annex No.1); B2 has appointed 2 staff (local coordinator and local accountant) by order B-457 of 2019-04-13 (Annex No.2); B3 has appointed 2 staff (local coordinator and local accountant) by order D46/345 of 2019-04-22 (Annex No.3). Project management group (PMG) is formed of 4 project staff members, namely, project manager and information specialist of LB, local coordinator and accountant of each B2 and B3, by LB order No. SR-31 of 2019-04-24 (Annex No.3a). Project Steering Group (PSG) has been formed consisting of one representative of each Beneficiary organisation and LB project manager (4 persons in total), orders of PSG members appointment for the project are issued by the Beneficiaries' organisations: LB order No. SR-21 of 2019-04-04 (Annex No.4), B2 order No. B-456 of 2019-04-12 (Annex No.5), B3 order No.D45/345 of 2019-04-21 (Annex No.6). PMG was organized on 15 May 2019 in Daugavpils, lasted for 6 hours and was attended by each Beneficiary, in total 4 project staff. Topics: project implementation progress and faced deviations, budget amendments, preparation of the progress report, activities for the next reporting period. Photos, List of participants, agenda and minutes of the meeting attached (Annex 7). PSG was organized on 08 August 2019 in Orsha, lasted for 5 hours and was attended by one representative of each Beneficiary and LB project manager, in total 4 participants. Topics: project implementation progress and budget overview, delay of construction works procurement, organizational and financial aspects of projects large summer events. Photos, List of participants, agenda and minutes of the meeting attached (Annex 8). | Project management group formed of 4 project staff members | 1
|  | Project Steering Group formed of 4 members | 1
|  | PMG meeting in Daugavpils (4 participants, 6 hours) | 1 | PMG meeting in Kupiškis (4 participants,6 hours) | 1
|  | PSG meeting in Orsha (3 participants, 5 hours) | 1 | PSG meeting in Daugavpils (4 participants, 5 hours) | 1
Activity 1.2 Internal monitoring and reporting procedures | Example. Overall management and administration of the project had been organized by LB with assistance of B2, B3. Implementation of the project activities had been supervised by the LB project manager; B2 and B3 project coordinators were responsible on coordination of local project activities, announcement of the procurements. LB project manager assistant ensured project implementation of LBs local project activities. LB information manager had ensured project publicity activities according to project description and Programme communication guidelines, cooperated with the JTS branch offices and B2, B3 local coordinators. Overall financial management of the project ensured by LB financial manager by following-up budget documentation, by executing LB’s and EU grant payments, information for financial report prepared. B2, B3 project accountants ensured local project financial management. Day-to-day management and internal monitoring of the project ensured by the LB through regular communication via e-mails, phone/skype and partners` visits. The B2 and B3 procured the services of the auditing companies. Each beneficiary provided individual report to the auditors, consisting of narrative and financial information. B2 and B3 supported LB in drawing up the consolidated progress report, produced and delivered all the information for reporting purposes to the LB. LB with assistance of B2 and B3 prepared and submittted to the JTS the consolidated progress report, followed-up budget documentation, and handled 1 request for amendments. LB, B2 and B3 sent the drafts of the communication materials to the relevant officers of the JTS for approval. | Individual beneficiaries reports submitted to auditors | 3 | Individual beneficiaries reports submitted to auditors | 3
|  | Consolidated progress report | 1 | Consolidated progress report | 1
Deviations from the initially planned activity and their reason/justification
* If within the reporting period due to a justified reason an activity initially planned to be implemented within this reporting period has not been implemented/ has been transferred to the next reporting period(s) or slightly modified with impact on the budget, describe the reason and indicate when it is planned to be implemented * Indicate deviations due to procurement (e.g. the reason the procurement was not started, the contract was not signed).
Example: 1) The number of participants in the Project management group (PMG) meeting was not 4 as originally planned, but 5 - additionally the procurement specialist and the engineer took part to explain the rules of the procurement. This did not affect the costs related to the meeting. 2) PSG meeting on 08 August 2019 in Orsha was shorter than planned (5 hours instead of planned 8 hours). This did not affect the efficiency of the meeting, as 5 hours was sufficient to decide on all the planned issues in agenda.
Changes in the Project staff
* If there were changes in the Project staff (project manager, financial manager or contact person) within the reporting period, indicate positions changed and a reason for changes.
* NB: an informative letter NOTIFICATION (please see the procedure described in the Guidelines Section 3.6) with a detailed information on the changed staff members (name, surname, phone/mobile phone number, e-mail) must be submitted to the JTS timely
Example: As of September 19, 2019, LB PM- Mr xxx. was replaced by Ms. Xxx, as the employment contract with Mr XXX was terminated. Ms. Xxx has similar qualifications, good knowledge of English and is appropriate for project management.
1.2 The second group of activities (GA2)
Planned activities | Activities implemented within the reporting period | Outputs produced within the current reporting period Outputs are immediate products of the project activities: tangible goods, services and infrastructure that activities produce |  | Outputs planned for the next reporting period Planned outputs for next 6-months reporting period, NOT all remaining outputs until the end of the project
|  | Description of related outputs | Number of outputs | Description of related outputs | Number of outputs
| Describe briefly the activity implemented within the reporting period (what was done, by whom, where, when and how it was implemented). Indicate the involved beneficiaries and participants. In case of events (workshops/seminars/festivals etc.) also indicate general issues/topics discussed /agenda of the event. * When reporting activities, use the style and language as in the Project Description. * In case of construction works or procurement of equipment, in case not finalised, please indicate the progress within the particular reporting period and from the beginning of the project in percentage | * Outputs shall be taken from respective sections of the Project Description. Please strictly use outputs how they are indicated in the Project Description. * Indicate here only the achieved outputs during the reporting period * If you need to include additional characteristics, please mark them in the brackets | * Indicate the full (whole) number of outputs produced, not a fraction (e.g., not 0,5 if 1 is planned) | * Indicate only those outputs, which are planned to be achieved in full within next 6-months reporting period, NOT partly or planned just to be started. * Planned outputs shall correspond to the Project Description. | * Indicate full number of outputs to be produced, not a fraction (e.g., not 0,5 if 1 is planned)
Activity 2.1 Promotional campaign of project activities and achievements | B2 published 1 article "The neighbours share common interests" in the newspaper "Arshanskaya Prauda" on 2019-08-31, which has 12 000 target subscribers. The purpose was to announce the launch of the project and provide publicity to the 1st event - A joint exhibition of local artists and craftspeople "Crafts through centuries". The rest 13 000 copies were sold at kiosks "Soyuzpechat" and other retail points. In total, 25000 people were informed. This includes local residents including the ones from Orsha District, as well as, the tourists from other regions. Although it is not possible to identify who exactly viewed the information but it is logical that everybody who viewed this information are the members of at least one project target group (Annex No.9). B3 on 2019-06-04 published 1 article "Bendradarbiavimas per sieną - renginys Kupiškio Dvare" in the local newspaper "Mano Kupiškis" which had a circulation of 10 000. It is distributed among the local residents of Kupiškis municipality, as well as tourists coming to Kupiškis. The purpose was to announce the launch of the project and provide publicity to the 1st event - tourism promotion event "Life of Medieval Manor". Although it is not possible to identify who exactly read the information but it is logical that everybody, who read it, are the members of at least one project target group (Annex No.10). | articles in the newspaper | 2 | articles in the newspaper LB,B2 | 2
| LB published 1 news update on its web-site: 2019-05-10 "Pošvaļdeibys puorstuovji pīsadola projekta „Myusu viesturiskais montuojums“ atkluošonys pasuokumā Oršā, Boltkrīvejā" (Annex No.11) https://www.daugavpils.lv/go.php/lv/projekti/67405/ The news update included information about the start of the project, EU and programme co-financing, planned major activities, events and achievements. Reffering to the analytics of the website, this update was viewed 326 times, which implies that 326 members of the target groups were reached by this information. This includes all groups (Daugavpils municipality local population, tourists, though it is not possible to identify who exactly viewed the information) B3 published 1 news update on its web-site: 2019-05-14 "Kupiškis pradeda naują projektą" (Annex No.12) https://www.kupiskis.lt/svetaine/33456/naujas_projektas The news update included information about the start of the project, EU and programme co-financing, planned major activities and achievements. Also it provided publicity for the 1st event - tourism promotion event "Life of Medieval Manor". Reffering to the analytics of the website, this update was viewed 175 times, which implies that 175 members of the target groups were reached by this information. This includes all groups (Kupiskis municipality local population, tourists, though it is not possible to identify who exactly viewed the information) | news update on the the web-site | 2 | news update on the web-site | 7
| B2 published 2 publications on their social networks (Facebook): 1) 2019-08-30: „Opening of the Joint Exhibition“(Annex No.13) with announcement, agenda and poster of a joint exhibition "Crafts through centuries" https://www.facebook.com/orshamuseum/photos/pcb.212591957436322/21259194943133567/?type=3&theater; 2) 2019-10-02: „Closing of the joint exhibition – new impressions“ (Annexes No.14), with the report of the exhibition and the photo gallery: https://www.facebook.com/orshamuseum/photos/pcb.2125919574364456/21259194943134338/?type=3&theater; Publications on facebook were viewed 449 times (publications No.1 - 205, publication No.2 - 244) , they collected 287 comments (99 and 188 respectively) and 151 Likes (71 and 80 respectively). This includes local residents including the people from Orsha District and all the Republic of Belarus, as well as the tourists from other regions. Though it is not possible to identify who exactly viewed the information but it is logical that all visitors who viewed this information are the members of at least one project target group. | news updates on beneficiaries social networks | 2 | news updates on the beneficiaries social networks | 18
| The temporary billboards were designed and placed at the construction site by the contactors of LB (Annex No.15) and B2 (Annex No.16). Producing of the billboard was not financed from the project budget. | temporary billboard | 2
n | Stickers for labelling of equipment (20) were made by B3 (Annex No.17). Due to small amount no procurement was needed, no costs were incurred or included to the report. Stickers for labelling of equipment (124) were purchased by B2 (Annex No.18). | stickers for labelling of equipment for LB3 (20 stickers), B2 (124 stickers) | 144
| Newsletter (Annex 19) for specialists in culture and tourism (guides, staff of cultural centres, museums and Tourism information centre, etc.), for specialists in historical and cultural heritage, actors, crafts people) with information about the project, upcoming activities, achievements, possiblities to participate was prepared in Latvian, Lithuanian, Russian languages and circulated to the 291 identified specialists (122 in Latvia, 87 in Lithuania, 82 in Belarus). | newsletter in LV, LT, RU languages | 1 | newsletter in LV, LT, RU languages | 1
| 3 Project posters were placed at the Beneficiaries' premises, 1 in each premise in LV, LT, BY, in Latvian, Lithuanian, Russian languages (Annex 20). The posters are aimed at visitors (local population, tourists) and the employees fo the Beneficiaries (culture and heritage specialists). They were placed at the entrance on the notice board to be visible to the visitors. The posters include general information about the project, main activities, EU and Programme contribution to the project. They were printed by each Beneficiary itself, no costs were charged to the project. | 3 project posters in Latvian, Lithuanian, Russian placed in Beneficiaries premises | 3
Target groups (including vulnerable groups) |  | Problems solved or needs met |  | Quantification | No. of Activity
* If the project is targeted at involvement of the particular target groups, describe which group(s) were involved within the reporting period. In case of Priority 1.1 and 1.2 indicate also which vulnerable groups were targeted. |  | * Describe what needs of the group were met or problems were solved within the activity |  | * Indicate the number of representatives of the group(s) that were involved during the reporting period only | * Indicate the number of related activity
TG1: Local population and tourists of Daugavpils municipality, Kupiskis municipality and Orsha District. |  | Local population and tourists were informed about project progress, the upcoming events within the framework of the project, about the events which were implemented, crossborder cooperation, project outputs produced so far and the EU co-financing to the project. They were informed about the construction works in Daugavpils Culture house and when they will be completed. |  | 35950 of them in Latvia 326, in Lithuania 10 175, in Belarus 25 449. (In LV, 326 visitors viewed information on the LB web-site. In LT, maximum 10 000 received the newspaper with the printed article, 175 visitors viewed information on the B2 web-site. In BY, maximum 25 000 received the newspaper with the printed article, 449 visitors viewed publication on the B3 Facebook) | 2.1
TG2: Specialists in culture and tourism (guides, staff of cultural centres, museums and Tourism information centre, etc.) Specialists in historical and cultural heritage, actors, crafts people) in Daugavpils municipality, Kupiskis municipality and Orsha District. |  | Specialists in historical and cultural heritage, actors, crafts people received the information about project progress, the upcoming events within the framework of the project, about the events which were implemented, the planned outcomes, facilities that were and will be developed and opportunities for development of culture and crafts potential, information about the joint exhibition in Orsha, tourism promotion event in Kupiskis, other events and activities that are planned within the framework of the project was also provided; the target groups were informed of the EU contribution to the project. |  | 291 (received and read the newsletter) | 2.1
Deviations from the initially planned activity and their reason/justification
* If within the reporting period due to a justified reason an activity initially planned to be implemented within this reporting period has not been implemented/ has been transferred to the next reporting period(s), describe the reason and indicate when it is planned to be implemented * Indicate deviations due to procurement (e.g. the reason the procurement was not started, the contract was not signed).
Example. 1) The Beneficiary 3 did not publish the news update about the project on its web-site, as due to change of Internet provider the web-site was not working properly. The news update will be published starting from the II Reporting period. 2) The Lead Beneficiary did not print the article in the newspaper, as it did not implement any significant cooperation activities or mass events for the target groups during the Ist Reporting period. The article will be published in the II Reporting period before organisation of the mass events.
1.3 The third group of activities (GA3)
Planned activities | Activities implemented within the reporting period | Outputs produced within the current reporting period Outputs are immediate products of the project activities: tangible goods, services and infrastructure that activities produce |  | Outputs planned for the next reporting period Planned outputs for next 6-months reporting period, NOT all remaining outputs until the end of the project
|  | Description of related outputs | Number of outputs | Description of related outputs | Number of outputs
| Describe briefly the activity implemented within the reporting period (what was done, by whom, where, when and how it was implemented). Indicate the involved beneficiaries and participants. In case of events (workshops/seminars/festivals etc.) also indicate general issues/topics discussed /agenda of the event. * When reporting activities, use the style and language as in the Project Description. * In case of construction works or procurement of equipment, in case not finalised, please indicate the progress within the particular reporting period and from the beginning of the project in percentage | * Outputs shall be taken from respective sections of the Project Description. Please strictly use outputs how they are indicated in the Project Description. * Indicate here only the achieved outputs during the reporting period * If you need to include additional characteristics, please mark them in the brackets | * Indicate the full (whole) number of outputs produced, not a fraction (e.g., not 0,5 if 1 is planned) | * Indicate only those outputs, which are planned to be achieved in full within next 6-months reporting period, NOT partly or planned just to be started. * Planned outputs shall correspond to the Project Description. | * Indicate full number of outputs to be produced, not a fraction (e.g., not 0,5 if 1 is planned)
Activity 3.1 Renovation of exhibition hall in the Daugavpils Culture House | Example. Renovation of the exhibition hall of 111,13 m2 in the Daugavpils Culture House of LB was started in order to improve the quality of culture events. Particular object as architectural monument is a very popular cultural place among cultural professionals, young people, Daugavpils citizen and guests. | Renovated premises in the Daugavpils Culture House (Daugavpils Uzvaras str.17, LV by LB), 111,13 m2 of area | 0 | Renovated premises in the Daugavpils Culture House (Daugavpils, LV by LB), 111,13 m2 of area | 1
The procurement procedure for works was implemented and was successful. The works implemented during 1st reporting period: wall paint was restored on area 85 m2, new parquet was laid on 50 m2, and in auxiliary premises of the Main Hall wall paint was restored 36 m2, manhole of the historic lift and ventilation outputs were preserved), renovated 16 m2 of staircases, 35 m2 of the roof (photos of progress of works in Annex 21). The amount of implemented works is 45,65%. The renovation works are not completed and will be finalised in the next Reporting period.
The LB procured services related to works: 1) Author supervision for the renovation of the exhibition hall was procured, to ensure that the construction works correspond to the technical documentation. 2) Technical supervision for the renovation of the exhibition hall was procured to ensure that the quality and quantities of the works correspond to the initial plan and cost estimates. Inspections by the Author supervision and Technical supervision were made, however the invoices were not provided during the Reporting period, according to the provisions of the concluded contracts.
Activity 3.2. Construction open-air stage in Kupiskis, LT B3 | Example. It is planned to construct open-air stage in Kupiškis (B3), total area 315 m2. The procurement of the construction works was started. The first procurement procedure started on 2019-09-29 was unsuccessful, and was cancelled. | Constructed open-air stage in Kupiškis (B3), total area 315 m2 | 0 | Constructed open-air stage in Kupiškis (B3), total area 315 m2 | 1
Activity 3.3 Purchase of sound, presentation and IT equipment, LT B3 | Example. 1) Procurement of a set of sound equipment for the organisation of the tourism promotion event "Life of Medieval manor" in Kupiskis has been started by B3. The B3 procured: 2 loudspeakers, 2 sub loudspeakers, 1 digital console, 1 equalizer, cables. Photos of the equipment with Programme visibility elements attached (Annex 22). | Set of sound equipment (2 loudspeakers, 2 sub loudspeakers, 1 digital console, 1 equalizer, cables) by B3 | 1
| 2) Due to delay with procurement of the open-air stage (activity 3.2) where the presentation equipment will be installed and need to change the documentation for works, procurement of a set of lighting, presentation and IT equipment as 1 projector, 1 screen, 1 tablet computer, 10 scenic flood lights was not implemented during the this Reporting period and was postponed to the next Reporting period. |  |  | Set of presentation and IT equipment (1 stationary projector, 1 stationary screen, 1 tablet computer) and lighting equipment (10 scenic flood lights) by B3 | 1
Activity 3.4 Renovation of cultural facilities in Orsha, BY B2. | Example. Procurement of Renovation works for 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha was implemented sucessfully, the contract was concluded. The works started on 2019-07-15. During the reporting period, 36,71% of works were implemented: 28 m2 of walls were plastered and painted, 31 m2 of floors were renovated, 4 heaters and 4 windows were replaced. Stairs in the staircase were improved (Annex 23). | Cultural object - 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha - renovated | 0 | Cultural object - 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha - renovated | 1
Activity 3.5. Purchase of furniture, BY B2 | Example. Furniture (13 tables 1x2m, 70 chairs, 7 sofas, 27 lamps, 7 decorative screens for heating elements) has been purchased for 2 exhibition halls and service rooms for Orsha History Museum by B2. Photos of the equipment with information plates in exhibition halls, where equipment located, attached (Annex 24). | Furniture (13 tables 1x2m, 70 chairs, 7 sofas, 27 lamps, 7 decorative screens for heating elements) by B3 | 124
Target groups (including vulnerable groups) |  | Problems solved or needs met |  | Quantification | No. of Activity
* If the project is targeted at involvement of the particular target groups, describe which group(s) were involved within the reporting period. In case of Priority 1.1 and 1.2 indicate also which vulnerable groups were targeted. |  | * Describe what needs of the group were met or problems were solved within the activity |  | * Indicate the number of representatives of the group(s) that were involved during reporting period only | * Indicate the number of related activity
TG1: Local population and tourists of Daugavpils municipality, Kupiskis municipality and Orsha District. |  | The purchased equipment contributed to better quality of cultural events in Kupiskis municipality and Orsha district. It has improved tourism infrastructure, quality of tourism services, contributed to attraction of tourists. 150 LT participants (spectators) representing the local population and tourists benefitted from better sound equipment, purchased within the activity 3.3 and used during the tourism promotion event "Life of Medieval Manor" in activity 4.2. In BY 1851 participants (spectators) representing the local population and the tourists benefitted from better furniure purchased within the activity 3.5 and used for organisation of joint exhibition of local artists and craftspeople "Crafts through centuries" in activity 4.3. |  | 2001 | 3.3, 3.5
TG2: Specialists in culture and tourism (guides, staff of cultural centres, museums and Tourism information centre, etc.) Specialists in historical and cultural heritage, actors, crafts people) in Daugavpils municipality, Kupiskis municipality and Orsha District. |  | The purchased equipment contributed to bigger variety of cultural events, organisation of new cultural activities in Kupiskis municipality and Orsha district. It has improved the conditions of work of the specialists in culture and tourism, facilitated planning, implementation of cultural activities and events. 10 LT specialists in culture and tourism (employees of B3) benefitted from using the better sound equipment, purchased within the activity 3.3 and used it during the tourism promotion event "Life of Medieval Manor" in activity 4.2. In BY 13 specialists in culture and tourism (employees of B2) benefitted from using better furniure purchased within the activity 3.5 and used it for organisation of joint exhibition of local artists and craftspeople "Crafts through centuries" in activity 4.3. |  | 23 | 3.3, 3.5
Deviations from the initially planned activity and their reason/justification
* If within the reporting period due to a justified reason an activity initially planned to be implemented within this reporting period has not been implemented/ has been transferred to the next reporting period(s), describe the reason and indicate when it is planned to be implemented * Indicate deviations due to procurement (e.g. the reason the procurement was not started, the contract was not signed).
Example. 1) The implementation of Activity 3.2 related to construction of open-air stage in Kupiškis (B3), total area 315 m2 by B3 is delayed, because of unsuccessful procurement of the works by B3. The changes to the construction documentation are prepared (replacement of materials for cheaper ones, change of places of installation of equipment) in order to reduce the cost of works, the request for amendments will be sent to the JTS. Documents are being prepared for the new procurement, it will be started in the next Reporting period. 2) Activity 3.3 related to procurement of sound, presentation and IT equipment for B3 was not implemented in full during this Reporting period. Reason: due to unsuccessful procurement of the construction works for the open-air stage in Kupiskis (activity 3.2) where the presentation equipment will be installed, the technical documentation shall be changed; the changes will include reallocation of places of installation of the flood lights, stationary presentation screen and presentation projector. When the new places of installation will be known, the technical characteristics of the stationary presentation screen and presentation projector will be updated, the procurement will be implemented and finalised during the next Reporting period. As well, the procurement of a set of sound equipment was implemented only partially, the B3 did not manage to procure 1 digital console, 1 equalizer, cables due to inappropriate technical characteristics proposed by the suppliers. The technical specifications will be adjusted, the procurement will be finalised in the next reporting period.
1.4 The fourth group of activities (GA4)
Planned activities | Activities implemented within the reporting period | Outputs produced within the current reporting period Outputs are immediate products of the project activities: tangible goods, services and infrastructure that activities produce |  | Outputs planned for the next reporting period Planned outputs for next 6-months reporting period, NOT all remaining outputs until the end of the project
|  | Description of related outputs | Number of outputs | Description of related outputs | Number of outputs
| Describe briefly the activity implemented within the reporting period (what was done, by whom, where, when and how it was implemented). Indicate the involved beneficiaries and participants. * When reporting activities, use the style and language as in the Project Description. | * Outputs shall be taken from respective sections of the Project Description. Please strictly use outputs how they are indicated in the Project Description. * Indicate here only the achieved outputs during the reporting period * If you need to include additional characteristics, please mark them in the brackets | * Indicate the full (whole) number of outputs produced, not a fraction (e.g., not 0,5 if 1 is planned) | * Indicate only those outputs, which are planned to be achieved in full within next 6-months reporting period, NOT partly or planned just to be started. * Planned outputs shall correspond to the Project Description. | * Indicate full number of outputs to be produced, not a fraction (e.g., not 0,5 if 1 is planned)
Activity 4.1 Organization of conferences, BY B2 | Example: The conference in Vitebsk“Cultural Heritage and Sustainable Development” was postponed for December 2019 as the potential participants could not participate due to being involved in the other Vitebsk Oblast events. | B2 Сonference in Vitebsk “Cultural Heritage and Sustainable Development” for 60 (20 LT, 20 BY, 20 LT) participants | 0 | B2 Сonference in Vitebsk “Cultural Heritage and Sustainable Development” for 60 (20 LT, 20 BY, 20 LT) participants | 1
|  | Conference and promotion materials: 80 notebooks, 80 pens, 80 badges, 80 programs, 80 folders, 90 pieces of the collection of conference materials | 0 | Conference and promotion materials: 80 notebooks, 80 pens, 80 badges, 80 programs, 80 folders, 90 pieces of the collection of conference materials | 490
4.2. Organisation of tourism promotion event, LT B3 | Example: The tourism promotion event "Life of Medieval Manor" was organized on the site of Kupiskis manor on 2019-06-13 by B2. It attracted 150 visitors (local population, tourists of manor, specialists in culture and tourism). The aim of the event was promotion of historical heritage of the region and stimulation of tourism. During the event, 4 historical performances were shown, 3 medieval dances were performed, 2 quests were organised. The event was free of charge. List of participants, photos, agenda, report of the event attached in Annex No. 25. The feedback about the event was collected referring to Facebook reactions (it was liked by 81 visitors on B2 Facebook profile and had 73 positive reactions on B2 Facebook account, Annex No.26). Following the results of the event, a survey of participants was conducted, information was posted on the website and in social media. 150 surveys have been distributed for workshop participants. 124 were returned. 82% of the respondents expressed the positive attitude towards the event, 12% neutral, 6% negative. Summary of survey - in Annex No.27. Catering and rent of equipment (costumes, medieval tools) was procured. 4 posters and 150 leaflets were made to promote the event and were distributed with the participants (Annex No.28). Designing of posters and leaflets, their printing were procured. | The tourism promotion event "Life of Medieval Manor" organized by B3, for 150 participants. | 1 | 0 | 0
|  | Leaflets for the the tourism promotion event "Life of Medieval Manor"" | 150 | 0 | 0
|  | Posters of the tourism promotion event "Life of Medieval Manor" | 4 | 0 | 0
4.3. Joint exhibition of local craftsmen and artist | Example: A joint exhibition of local artists and craftspeople "Crafts through centuries" was organised by B3 in Orsha. The purpose was the preservation and popularization of folk traditions, the promotion and development of traditional crafts in the border regions. The traditions of weaving and wood carving have been preserved by Belarusians, Latvians and Lithuanians to this day and can help in promotion of historical heritage of the cross border region. The exhibition featured 67 pieces of decorative weaving and 82 pieces of wood carving made by craftsmen from Latvia, Lithuania and Belarus. The opening ceremony of the exhibition was held on 2019-09-02, it was attended by 87 people; visitors participated in workshops on weaving and wood carving, as well as in traditional games and entertainment during the first 2 days of the event. The exibition lasted until 2019-10-02. The opening ceremony, the exhibition was free of charge. For the opening ceremony and first 2 days of the exhibition, the agenda, list of participants, photos, report are attached in Annex No.29. A total number of 1851 visitors attended the exhibition (of them, 451 foreign tourists). The pages of the registration journal are attached in Annex No.30. Catering and supplies, materials for art presentation were procured. Photos of the procured supplies and materials are attached in Annex No.31. One set of printed products were made for the exhibition (11 posters, 150 flyers, 250 stickers, 1 banner, 1 roll-up), Annex No.32. Reviews and evaluations from the visitors were collected by records in the Book of visitors. 72% of the visitors expressed positive evaluation, feedback from 21% was extremely positive. Summaries of evaluation, pages from the Book of visitors are attached in Annex No.33. | Joint exhibition of local artists and craftspeople took place in Orsha "Crafts through centuries" | 1
|  | Participans of Joint exhibition of local artists and craftspeople took place in Orsha "Crafts through centuries" 9LT/ 13BY /12 LV | 34
|  | Audience of Joint exhibition of local artists and craftspeople took place in Orsha "Crafts through centuries" | 1851
|  | 1 set of printed products for the exhibition (11 posters, 150 flyers, 250 stickers, 1 banner, 1 roll-up) | 1
Activity 4.4 Organising trainings for professioals in heritage and crafts | This activity was not planned to be implemented within the reporting period. | _ | _ | Training in Rhetoric and artistic language 1 seven-hour workshop (1 day 7 hours) | 1
|  | _ | _ | Training in Folk traditions 1 seven-hour workshop (1 day 7 hours) | 1
|  | _ | - | Training in Communication psychology 1 seven-hour workshop (1 day 7 hours) | 1
|  | _ | _ | Professionals in culture and heritage (15 LV, 19 LT, 21 BY) trained | 55
Target groups (including vulnerable groups) |  | Problems solved or needs met |  | Quantification | No. of Activity
* If the project is targeted at involvement of the particular target groups, describe which group(s) were involved within the reporting period. In case of Priority 1.1 and 1.2 indicate also which vulnerable groups were targeted. |  | * Describe what needs of the group were met or problems were solved within the activity |  | * Indicate the number of representatives of the group(s) that were involved during reporting period only | * Indicate the number of related activity
TG1: Local population and tourists of Daugavpils municipality, Kupiskis municipality and Orsha District. |  | Cultural and tourism services provided in Kupiskis municipality and in Orsha district have become more diversified and of better quality. Cultural and historical heritage (dances, crafts and artistic works) was used for cultural and tourism needs. The variety and quality of cultural services have improved. Two high quality new cultural services - cultural events in cultural heritage sites in Kupiskis and Orsha were offered to the local residents and tourists of Kupiskis municipality and Orsha District. 150 visitors in Lithuanian region and 1851 visitor in Belarusian region, belonging to local population and tourists were able to participate in cultural events in activities 4.2 and 4.3 and broadened their outlook regarding traditional crafts and culture. Their educational and cultural needs were satisfied. Events had positive effect on strengthening their national identity. Cultural heritage sites were promoted as attractive cultural venues. |  | 2001 | 4.2, 4.3
TG2: Specialists in culture and tourism (guides, staff of cultural centres, museums and Tourism information centre, etc.) Specialists in historical and cultural heritage, actors, crafts people) in Daugavpils municipality, Kupiskis municipality and Orsha District. |  | By organisation and implementation of the new activities 4.2 and 4.3, participation in these activities, the specialists in heritage and culture of the Beneficiaries 3 (9 specialists) and Beneficiary 2 (13 specialists), of the Lead Beneficiary (12 specialists) improved their qualification, developed new ideas of organisation of cultural activities, this contributed to bigger variety of cultural events in the municipalities. They practiced new solutions and approaches how to make use of cultural and historical heritage for the purposes of tourism development, promotion of local culture with the local residents. |  | 34 | 4.2, 4.3
Deviations from the initially planned activity and their reason/justification
* If within the reporting period due to a justified reason an activity initially planned to be implemented within this reporting period has not been implemented/ has been transferred to the next reporting period(s), describe the reason and indicate when it is planned to be implemented * If the activity or output was modified by Request for Amendments, please include information on approved minor or substantial amendments during reporting period (number of requests, dates of submission and approval, signature of Addenda, changed positions and reason for changes). * Indicate deviations due to procurement (e.g. the reason the procurement was not started, the contract was not signed).
Activity 4.1: The conference in Vitebsk“Cultural Heritage and Sustainable Development” planned to be implemented in October 2019. However it was postponed for December 2019 as the potential participants were involved in the other Vitebsk Oblast events, and only limited number could take part in the conference. Implementation of the conference at a later date would ensure sufficient quality of the activity. Activity 4.2: Initially it was planned that 10 specialists in heritage and culture of the Beneficiary 3 will be participating in the tourism promotion event, in fact - only 9 took part. 1 participant was not able to participate because of sick-leave. The quality of the event however was not reduced, as its functions were fulfilled by the other colleague. Acitivity 4.3: Instead of the originally planned 20 calendar days, the Joint Exhibition of local craftsmen and artists lasted for 1 month because it aroused a great interest among residents and visitors of Orsha District, which was repeatedly noted in the reviews of visitors.The time of its exposure was extended due to the great success.
1.5 The fifth group of activities (GA5)
Planned activities | Activities implemented within the reporting period | Outputs produced within the current reporting period |  | Outputs planned for the next reporting period
|  | Description of related outputs | Number of outputs | Description of related outputs | Number of outputs
_ | _ | _ | _ | _ | _
Target groups (including vulnerable groups) |  | Problems solved or needs met |  | Quantification | No. of Activity
_ |  | _ |  | _
Deviations from the initially planned activity and their reason/justification
1.6 Table of the communication outputs
Output | Number of Output | No. of copies / edition, circulation (if applicable) | Description of output |  | Activity (GA)
Indicate the produced communication output (e.g, article, brochure, memory plate, stand, audio/video material, press conference, etc.) *Outputs shall correspond to Project Description, section 5.7 | Indicate the number of the communication outputs, which were implemented/produced during the reporting period only (MM) | In case of published materials (e.g., articles, books, brochures, flyers, etc.), indicate their circulation. *Please follow the format in section 5.7 | Indicate detailed information on the produced output. In case of printed publications or audio/video materials, indicate their titles, when and where they were published/broadcast, how they were disseminated, how large the reached target audience was (number) and indicate a direct link (if available online) |  | Indicate the number of related activity
News updates on internet site | 2 | N/A | LB published 1 news update on its web-site: 2019-05-10 "Pošvaļdeibys puorstuovji pīsadola projekta „Myusu viesturiskais montuojums“ atkluošonys pasuokumā Oršā, Boltkrīvejā" (Annex No.11) https://www.daugavpils.lv/go.php/lv/projekti/67405/ Target audience: local population, tourists of Daugavpils municipality. Reached audience: Reffering to the analytics of the website, this update was viewed 326 times, which implies that 326 members of the target groups were reached by this information. This includes all groups (Daugavpils municipality local population, tourists, though it is not possible to identify who exactly viewed the information). The news update included information about the start of the project, EU and programme co-financing, planned major activities, events and achievements. B3 published 1 news update on its web-site: 2019-05-14 "Kupiškis pradėda naujas projektas" (Annex No.12) https://www.kupiskis.lt/svetaine/33456/naujas_projektas Target audience: local population, tourists of Kupiskis municipality. Reached audience: Reffering to the analytics of the website, this update was viewed 175 times, which implies that 175 members of the target groups were reached by this information. This includes all groups (Kupiskis municipality local population, tourists, though it is not possible to identify who exactly viewed the information). The news update included information about the start of the project, EU and programme co-financing, planned major activities, and achievements. Also it provided publicity to the 1st event - tourism promotion event "Life of Medieval Manor". |  | 2.1.
Publications in social networks accounts | 2 | N/A | B2 published 2 publications on their social networks (Facebook): 1) 2019-08-30: „Opening of the Joint Exhibition“ with announcement, agenda and poster of a joint exhibition "Crafts through centuries" (Annex No.13) https://www.facebook.com/orshamuseum/photos/pcb.212591957436322/21259194943133567/?type=3&theater; It collected 211 views, 101 comments, 49 Likes. 2) 2019-10-02: „Closing of the joint exhibition – new impressions“ (Annex No.14), with the report of the exhibition and the photo gallery: https://www.facebook.com/orshamuseum/photos/pcb.2125919574364456/21259194943134338/?type=3&theater; It collected 238 views, 186 comments, 102 Likes. Target audience: local population, tourists of Orsha District. Publications on facebook were viewed 449 times (publications No.1 - 205, publication No.2 - 244) , they collected 287 comments (99 and 188 respectively) and 151 Likes (71 and 80 respectively). This includes local residents including the people from Orsha District and all the Republic of Belarus, as well as the tourists from other regions. Though it is not possible to identify who exactly viewed the information but it is logical that all visitors who viewed this information are the members of at least one project target group. |  | 2.1
Article in the national/local newspaper | 2 | 35000 | B2 published 1 article "The neighbours share common interests" in the newspaper "Arshanskaya Prauda" on 2019-08-31. The purpose was to announce the launch of the project and provide publicity to the 1st event - A joint exhibition of local artists and craftspeople "Crafts through centuries". Target audience: local population, tourists of Orsha District. Reached audience and distribution: local residents including the ones from Orsha District, as well as the tourists. 12000 subscribers received the newspaper, the rest 13 000 copies were sold at kiosks "Soyuzpechat" and other retail points. In total, 25000 people were informed. Although it is not possible to identify who exactly viewed the information but it is logical that everybody who viewed this information are the members of at least one project target group (Annex No.9). B3 on 2019-06-04 published 1 article "Bendradarbiavimas per sieną - renginys Kupiškio Dvare" in the local newspaper "Mano Kupiškis". The purpose was to announce the launch of the project and provide publicity to the 1st event - tourism promotion event "Life of Medieval Manor". Target audience: local population, tourists of Kupiskis municipality. Reached audience and distribution: local residents including the ones from Kupiskis municipality, as well as the tourists. The newspaper had a circulation of 10 000, all issues were sold. It is distributed among the local residents of Kupiškis municipality, as well as tourists coming to Kupiškis. Although it is not possible to identify who exactly read the information but it is logical that everybody, who read it, are the members of at least one project target group (Annex No.10). |  | 2.1
Newsletter for specialists in culture and tourism | 2 | N/A | Newsletter for specialists in culture and tourism (guides, staff of cultural centres, museums and Tourism information centre, etc.). Target audience: specialists in historical and cultural heritage, actors, crafts people in Daugavpils municipality, Kupiskis municipality, Orsha District. Target audience reached, dissemination: the text prepared jointly in English and translated into Latvian, Lithuanian, Russian. The newsletter was circulated to the 291 identified specialists (122 in Latvia, 87 in Lithuania, 82 in Belarus). The newsletter included information about the project, upcoming activities, achievements, invitation and possiblities to participate in project activities. The newsletter in 3 languages, the proof of sending is provided in Annex No.19. |  | 2.1
Posters | 3 | N/A | 3 Project posters were placed at the Beneficiaries' premises, 1 in each premises in LV, LT, BY, in Latvian, Lithuanian, Russian (Annex No.20). Target audience - visitors (local population, tourists) and the employees fo the Beneficiaries (culture and heritage specialists). They were placed at the entrance on the notice board to be visible to the visitors. The posters include general information about the project, main activities, EU and Programme contribution to the project. |  | 2.1
Stickers | 144 | N/A | Stickers for equipment with programme visibility elemets, by B3 (20) in Annex No.17 and by B2 (124) in Annex No.18. They were and will be used for marking of the purchased equipment . Target audience - visitors (local population, tourists) and the employees fo the Beneficiaries (culture and heritage specialists). |  | 2.1
4 Posters of the tourism promotion event "Life of Medieval Manor" | 1 | 4 | Posters (Annex No.28) were placed near the public buildings in Kupiskis to publicise the event and invite the potential participants. Target audience - visitors (local population, tourists), they helped to ensure participation of the necessary number of participants (150). The posters include agenda of the event, general information about the project, EU and Programme contribution to the project. |  | 4.2
150 Leaflets (LT) for the tourism promotion event "Life of Medieval Manor" | 1 | 150 | Leaflets (Annex No.28) were distributed fo the participants of the event. Target audience - visitors (local population, tourists), they helped to ensure participation of the necessary number of participants (150). The leaflets include agenda of the event, general information about the project, EU and Programme contribution to the project. |  | 4.2
1 set of printed products for the exhibition "Crafts through centuries" (11 posters, 150 flyers, 250 stickers, 1 banner, 1 roll-up) | 1 |  | The printed products (Annex No.32) were used to publicise the event. Banner and roll-up were placed in the exhibition premises and posters were placed in the public buildings to inform about the event and the EU contribution. Flyers and stickers were distributed fo the participants of the event. Target audience - visitors (local population, tourists), they helped to ensure participation of the necessary number of visitors (1851). The leaflets include information about the event, general information about the project, EU and Programme contribution to the project. |  | 4.3
Temporary billboard | 2 |  | The temporary billboards were designed and placed at the construction site by the contactors of LB and B2. They provide information about the construction works, the project itself and that the EU contribution. Producing of the billboard were not financed from the project budget. (Annexes No.15 and No.16). Target audience - visitors (local population, tourists) and the employees fo the Beneficiaries (culture and heritage specialists). |  | 2.1
2.7 External/internal problems and counter measures taken
External/internal problems *Describe internal and external problems or difficulties in implementation which occurred within the reporting period. |  | Counter-measures undertaken *Provide the information about the counter-measures undertaken by the Lead Beneficiary and Beneficiaries to overcome the problems or difficulties
Regarding activity 1.1 "Management and Coordination", internal problem:
The procurement specialist of Beneficiary 2 did not have sufficient understanding of the procurement rules of the Programme. Therefore,she made mistakes in preparation of the procurement documentation, this delayed announcement of the tender and affected its outcomes. |  | Lead Beneficiary and Beneficiary 3 provided assistance and consultation regarding preparation of the procurement documentation and implementation of the procurement. They also recommended to involve a specialist with knowledge of the best international practice in procurement, knowledge of English. The Beneficiary 2 agreed and will involve such specialist in the next Reporting period.
Regarding activity 3.2 "Construction open-air stage in Kupiskis, LT"
The implementation of Activity 3.2 related to construction of open-air stage in Kupiškis (B2), total area 315 m2 by B3 is delayed, because of unsuccessful procurement of the works by B3; the unsuccessful procedure was cancelled. |  | The changes to the construction documentation are being prepared (replacement of materials for cheaper ones, change of places of installation of equipment) in order to reduce the cost of works, the request for amendments will be sent to the JTS. Documents are being prepared for the new procurement, it will be started in the IInd Reporting period. In new procurement documentation the Contractor will be requested to finalise the works until the end of the project. As well, after the contractor is selected, the B3 will implement all necessary measures to ensure smooth implementation of the works and their finalisation until the end of the project. The progress of the works will be constantly supervised by the technical and author supervisions, problems will be solved by the technical supervision as soon as possible. Beneficiary 3 will ensure uninterrupted financial flow to pay for the works.
Regarding activity 3.3 "Purchase of sound, presentation and IT equipment"
The characteristics of the presentation equipment depend on parameters of the open-air stage. Due to delay with procurement of the open-air stage (activity 3.2) where the presentation equipment will be installed and due to a need to change the technical documentation for works which can affect the parametres of the open-air stage, location of the presentation equipment and its functioning, procurement of a set of presentation and IT equipment as 1 projector, 1 screen, 1 tablet computer was not implemented during the current Reporting period and was postponed to the next Reporting period. |  | After the technical documentation for works is changed, procurement implemented and Contractor is selected, it will be fixed what will be the parametres of the open-air stage to be constructed. According to these parametres (including the place of location of the presentation equipment, screen, distance from the projector to the screen, lightening, etc.), the technical specifications for the equipment will be adjusted, procurement will be announced, and implemented.
If it is not obvious or straightforward how the number was calculated, please provide explanations.
Direct working link to the publication shall be provided. Data from the analytics shall be provided, and analytics of visitors shall be submitted.
In reporting of the publications in media, important information shall be provided: date, newspaper/portal, purpose of the publication or main message, readership (target groups reached), channels of dissemination.
Prior to make them public, the drafts and/or plans of each information or promotion output or activity have to be agreed with the Communication specialists of the JTS.
If the activity was implemented not as originally planned (but with the deviations), including the timing, duration, number of participants, please explain this in the section related to the Deviations.
Indicate each output in a separate cell, in the same row as achieved respective output within the reporting period
It shall be explained how the project management (thematic, financial), reporting, internal communication was implemented.
In case of the 1st Reporting Period, please indicate the internal legal acts (Orders) regarding allocation of staff to the project and creation of the Project management bodies, e.g., Steering Committee, Project management group and allocation of Beneficiaries' employees to them.
It is recommended to highlight the Annexes in bold so that they are visible and easy to find, to show that the activity/output is supported by the documents. It is recommended to put the number of the annex after mentioning of the respective document, ouput or activity.
The number of the Annexes in the Activity Description shall correspond to the ones in section 10 "Annexes".
Indicate each output in a separate cell
Please include clarifications where the situation might be potentially unclear.
Achieved output, in this particular case (works) means "accepted into exploitation", if required under the law, or finalised as renovation in accordance with the law.
All major procurements shall be done as early as possible.
If the calculation of the target groups who benefited is not straightforward or obvious, please provide explanation, how they were calculated.
Please provide realistic and working counter-measures to solve the problem and ensure finalisation of the activity on time.
Please note: the partnership shall be strongly committed to solve all the problems in implementation, to fulfill all the activities and reach all the indicators within the project.
In case the partnership planned to purchase numerous equipment, but didn’t finish purchasing within one period, the procured equipment shall be listed in the section "Activities implemented within the reporting period" as procured wihtin the reporting period. In the activity description it shall be indicated the % or how many items were purchased. As well, planned to be procured within the next reporting period equipment shall be also indicated additionally.
All annexes shall be stored in order and their relation to the activities shall be indicated.
The number of the respective activity (e.g., Activity 2.2) should be indicated on the right top corner of the page in paper version of each Annex.
Direct working link to the publication shall be provided. If applicable, analytics shall be provided in Annexes, main data from the Analytics shall be described in the report.
If any output was not financed by the project, or free of charge, please indicate this clearly
If the activity was implemented not as originally planned (but with the deviations), including the timing, duration, number of participants, please explain this in the section related to the Deviations.
In case the planned outputs are not achieved within the next period, the respective clarifying information shall be added to the next report to the Section “Activities implemented within the reporting period” and/or “Deviations”. For all GAs.
In case the planned outputs are not achieved within the next period, the respective clarifying information shall be added to the next report to the Section “Activities implemented within the reporting period” and/or “Deviations”. For all GAs.
If the works or procurement of the equipment were not finalised during the reporting period (i.e. implemented partially), please describe the works implemented (or equipment purchased), and indicate the percentage of the implemented works (purchased equipment) in the description of the implemented activity.

## Logical Framework
2. LOGICAL FRAMEWORK
1. Provide an updated version of the Logframe matrix. Additional lines can be added for listing activities or outputs .
2. Take into account the information indicated in the report(s) and Project Description, when filling in the Logframe matrix.
3. See definitions below the Logframe matrix in order to fill it in correctly.
Results chain (What we want to achieve) |  | Indicators (How to measure change) | Contracted value (1) | Achieved within reporting period (2) | Achieved since the start date (cummulative) (3) | Progress (%) (4) 4=3/1x100% |  | Sources and means of verification (Where / how to get information) | Assumptions (What else to be aware of) To revise the assumptions and to adapt them to the factual situation
Overall objective: impact | To increase tourist flows in Daugavpils, Kupiskis, Orsha regions by enhancing the regions' cultural vitality and attractiveness. | In 5 years after the end of the project, the number of accommodated tourists per year in the participating regions increased by 15%. | Filled in Final Report only | Contribution is shown in Final report only. | Contribution is shown in Final report only. | Contribution is shown in Final report only. | remove years | Official statistical data of Daugavpils municipality, Kupiskis municipality, Orsha district.
Specific objective(s) (So): Results (outcomes) | To ensure more sustainable and effective use of cultural and historical heritage for tourism purposes in the cross-border region. | Increased number of cultural events participants in the Daugavpils municipality, Kuipskis municipality and Orsha district by 3800 persons by the end of the project. | 3800 | 2001 | 2001 | 52.66% |  | Project reports. Photographs. List of Participants. Feedback surveys. Official statistical data of Daugavpils municipality, Kupiskis municipality, Orsha district. Internal documents of the Beneficiaries regarding introduction of new cultural services, plans and agendas. | National and local authorities‘ policies and measures to promote tourism and culture remain the same or improve. There are sufficient budgetary allocations from public budget to ensure durability of activities. The economic situation remains favourable for development of tourism, culture and crafts. Visa regime remains the same or is facilitated. Public image of tourism and promotion of local culture remains positive.
|  | Increased number of services, cultural activities in cultural heritage sites in Daugavpils municipality, Kuipskis municipality and Orsha district by 7 events/services/activities by the end of the project. | 2 | 2 | 2 | 100%
|  | Professionals in the fields of culture, cultural and historical heritage and tourism who improved their professional skills by the end of the project (persons). | 113 | 34 | 34 | 30.09%
|  | Number of tourists accommodated per 1000 of population in the Daugavpils municipality, Kuipskis municipality and Orsha district has increased from 38,85 (year 2016) until 43,61 by year 2022, i.e. by 12,25% or by 4,76 persons. | 43.61 | 0 | 0 | 0%
Outputs | Promotional campaign of project activities and achievements (GA2) | Articles in newspapers (2 LV, 5 LT, 2 BY) | 9 | 2 | 2 | 22.22% |  | Project reports, websites, Photographs, print-outs. Articles in the press. | The economic situation remains favorable for development of tourism, culture and crafts. The target groups (Professionals of cultural and tourism field, tourists and local population) are properly informed, sufficiently interested, motivated to promote cultural and historical heritage and traditional skills, and to participate further in the cultural, historical activities, traditional skills events. The target groups (professionals in culture and tourims) are sufficiently motivated to share their experience and accept innovation
|  | News updates (4 News updates on 3 internet sites (LB, B2, B3) | 12 | 2 | 2 | 16.67%
|  | News updates (6 News updates on 3 social networks accounts (LB, B2, B3)) | 18 | 2 | 2 | 11.11%
|  | Newsletters for professionals (in Latvian, Lithuanian, Russian) - 6 in three languages | 6 | 2 | 2 | 33.33%
|  | Temporary billboard (1 LB, 1 B2, 1 B3) | 3 | 2 | 1 | 33.33%
|  | Permanent plaque (1 LB, 1 B2, 1 B3) | 3 | 0 | 0 | 0%
|  | Notebooks with visibility elements (110 by B3) | 110 | 110 | 110 | 100%
|  | Promotional video (3 min) (LB) | 1 | 0 | 0 | 0%
|  | 3 project posters in Latvian, Lithuanian, Russian placed in Beneficiaries premises | 3 | 3 | 3 | 100%
|  | Stickers for equipment 20 B2, 124 B3 | 144 | 144 | 144 | 100%
| Cultural facilities and heritage sites adapted to meet the cultural and tourism needs (GA3). | Renovated premises in the Daugavpils Culture House (Daugavpils, LV by LB), 111,13 m2 of area | 1 | 0 | 0 | 0% |  | Project reports. The documents of commissioning into exploitation and registration. Photographs.
|  | Constructed open-air stage in Kupiškis (B2), total area 315 m2 | 1 | 0 | 0 | 0% |  | Project reports. The documents of commissioning into exploitation and registration. Photographs.
|  | Set of sound equipment (2 loudspeakers, 2 sub loudspeakers, 1 digital console, 1 equalizer, cables) by B2 | 1 | 1 | 1 | 100% |  | Project reports. The acts of acceptance of transfer. Photographs.
|  | Set of presentation and IT equipment (1 stationary projector, 1 stationary screen, 1 tablet computer), lightening equipment (10 flood lights) by B3 | 1 | 0 | 0 | 0%
|  | Cultural object - 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha - renovated | 1 | 0 | 0 | 0% |  | Project reports. The documents of commissioning into exploitation and registration. Photographs.
|  | Furniture (13 tables 1x2m, 70 chairs, 7 sofas, 27 lamps, 7 decorative screens for heating elements) by B2 | 124 | 124 | 124 | 100% |  | Project reports. The acts of acceptance of transfer. Photographs.
| New and improved cultural and tourism services in cultural heritage sites. Joint cross-border cultural events (GA4) | Cultural events (1 in Lithuania, 1 in Belarus) | 2 | 2 | 2 | 100% |  | Agendas, photos, memo/reports of the events, announcements, posters. Feedback surveys
|  | Cultural events paticipants in Belarus | 34 | 34 | 34 | 100% |  | Lists of participants, photos
|  | Audience of cultural events - 3800 | 3800 | 2001 | 2001 | 52.66%
|  | Sets of promotion materials for event in Lithuania | 1 | 1 | 1 | 100% |  | Project reports. The acts of acceptance of transfer. Print-outs. Photographs.
|  | Set of printed materials for the exhibition in Belarus | 1 | 1 | 1 | 100%
|  | Conferences in Vitebsk for 60 professionals in culture and heritage, by B3 | 1 | 0 | 0 | 0% |  | Agendas, photos, memo/reports of the events, announcements, posters. Feedback surveys
|  | Set of Conference and promotion materials: 80 notebooks, 80 pens, 80 badges, 80 programs, 80 folders, 90 pieces of the collection of conference materials | 1 | 0 | 0 | 0% |  | Project reports. The acts of acceptance of transfer. Print-outs. Photographs.
| Joint training events for cultural and tourism professionals (GA4) | Trainings for professionals in culture and heritage | 3 | 0 | 0 | 0% |  | Agendas, photos, memo/reports of the events, announcements, posters. Feedback surveys
|  | Professionals in culture and heritage (15 LV, 19 LT, 21 BY) trained | 55 | 0 | 0 | 0% |  | Lists of participants, photos
Activities | GA 2 Activity 2.1. Promotional campaign of project activities and achievements | In total, from the start of the project, there were produced: 3 articles in press (out of 9 planned), 2 news updates on 2 internet sites (out of 12 planned), 2 publications in 2 social networks (out of 18 planned); 2 temporary billboard (of 3 planned), 144 stickers for equipment as planned. Beneficiary 2 produced 110 notebooks, all Beneficiaries placed 3 project posters in their premises, as this was planned by the project. | During the reporting period, the Beneficiaries published 2 articles in press (1 B2, 1 B3), 2 news updates on 2 internet sites (1 LB, 1 B2), 2 publications in 2 social networks (by B2). There were produced 2 temporary billboard for works (by LB), 144 stickers for equipment (20 by B3, 124 by B2). 2 newsletters in 3 languages (LV, LT, RU) were sent to professionals, 3 project posters were placed (1 for each Beneficiary). | [5 empty] | Pre-conditions: The mass media and suppliers are ready to cooperate. The technical condition, ownership and purpose of the 2 objects do not change and remain the same. The legal acts regulating construction works do not change and remain the same. The target groups (stakeholders, specialists in culture and historical heritage, tourists, local population) are sufficiently interested, motivated and can physically take part in project activities. Visa regime remains the same or is facilitated.
| GA3 Activity 3.1. Renovation of the Exhibition Hall in the Daugavpils Culture House | In total, from the start of the project, there were produced: 0 construction object (only 45,65% of the planned works finalised), 0 items of equipment (of 50 items planned) by Lead Beneficiary. | During the reporting period, the Lead Beneficiary procured and started the construction works for the Renovation of the Exhibition Hall in the Daugavpils Culture House (the works are at a level of readiness 45,65%), however did not procure any equipment.
| GA3 Activity 3.2. Construction of open air stage in Kupiskis, LT | In total, from the start of the project, 0 construction objects were produced. | During the reporting period, the Beneficiary 3 did not procure and did not start the works.
| GA3 Activity 3.3. Purchase of sound, lightening, presentation and IT equipment by B3 | In total from the start of the project, 1 set of equipment (sound) of the planned 2 was purchased by B3. | During the reporting period, the Beneficiary 3 purchased 1 set of sound equipment.
| GA3 Activity 3.4. Renovation of cultural facilities in Orsha, BY, by B2 | In total, from the start of the project, 0 construction objects were produced. | During the reporting period, the Beneficiary 2 did not procure and did not start the works.
| GA3 Activity 3.5. Purchase of furniture by B2. | In total, from the start of the project 1 multimedia projector, 124 items of furniture were purchased by B2, as planned. | During the reporting period, the Beneficiary 2 purchased 124 items of furniture.
| GA4 4.1. Organizing Conferences | In total, from the start of the project, 0 conferences were organised by B2. | The activity was not implemented during the reporting period.
| GA4 4.2 Organisation of tourism pomotion event | In total, from the start of the project, 1 tourism promotion event was organised by B3, as planned. | During the reporting period, the Beneficiary 3 organised 1 tourism promotion event "Life of Medieval Manor", for 150 participants; as well, it purchased a set of promotion materials for event (4 posters, 150 leaflets)
| GA4 4.3. Joint exhibition of local craftsmen and artists | In total, from the start of the project: 1 joint exhibition was organised by B2 in Orsha, as planned. | During the reporting period 1 joint exhibition of local craftsment and artists "Crafts through centuries" was organised by B2 in Orsha. In the event there participated 34 participants (9 from LT, 13 from BY, 12 from LV) and 1851 spectators. 1 set of printed products for the exhibition was produced.
| Act of GA4 4.4. Organizing training for professionals in heritage and culture | In total, from the start of the project 0 trainings for professionals were organised. | The activity was not planned to be implemented within the reporting period.
Definitions:
Overall objective - impact means the primary and secondary, long term effects produced by the Project.
Specific objective(s) -results (So) means the achieved direct short-term and medium-term effects of the project’s outputs.
Outputs (Op) mean the products, capital goods and services which result from the project's activities.
Activities (Act) mean the collection of tasks to be carried out in order to achieve the outputs.
Indicator is the quantitative and/or qualitative factor or variable that provides a simple and reliable means to measure the achievement of the results of the project.
Here provide the information how you collected information. E.g., for equipment an acceptancy act can be a source of verification, for website visitors - printout with statistics, for event - participants' list.
For 2nd, 3rd Progress reports, for Final Report: Check previous report and summarise values indicated in 2 and 3 columns. For 1st Progress report - there shall be the same values in 2nd and 3rd columns.
Start filling this table with transfering ALL indicators from your Grant Application Form section "Logical framework".
For each indicator use one separate line.
If in the Grant Application form a summary of indicators is provided for all partners, you can use a separate line for each partner.
If you started an infrastructure object, but have not finished yet (did not accept or commission into exploitation if required), do not indicate progress in % here, rather provide description in the descriptive part. Only fully completed infrastruture object shall be included here.
Provide brief summary how activity was implemented during the reporting period.
Provide brief summary how the activity was progressing from the start of the project.
This table is used for the monitoring of the project progress, thus it shall reflect situation not only for the particular reporing period, but also for all reporting periods, from the start of the project.
List all activities planned to be implemented within the project and set in the Grant Contract.

## Timetable
3. TIMETABLE
Provide an updated project plan for the future by marking the relevant boxes by X. This plan shall cover the period from the current progress report to the end date of the project.
GA | Title of GA | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 5 | Quarter 6 | Quarter 7 | Quarter 8
GA1 | Management and coordination | x | x | x | x | x | x | x | x
GA2 | Campaign to promote project activities and achievements | x | x | x | x | x | x | x | x
GA3 | Adapting of cultural heritage sites for cultural and tourism activities |  | x | x | x | x | x | x | x
GA4 | Joint cross-border cultural and training events |  |  | x | x | x | x | x | x
Please indicate actual and realistic timetable.

## Information on Procurement
4. INFORMATION ON PROCUREMENT PROCEDURES
List all contracts (works, supplies, services) above €3.000 (without VAT) awarded within the reporting period, the procurement procedures you have done for each type of the contracts, i.e., service, supplies and work contracts and the name of the contractor. Add as many rows as necessary.
Title of the contract, contractor and amount | Procurement procedure
Contract for works No.BUV-25 of 2019-10-01 with SIA „Construct-M“, cost of the contract 73 680,81 EUR including VAT (58207,84 EUR excluding VAT). Relates to: budget item 4.1, activity 3.1, Procurement plan point 34. | The procurement of renovation works of the exhibition hall in the Daugavpils Culture house was launched by the Lead Beneficiary 2 on 2019-08-15. Type of procedure: competitive negotiated procedure without publication.
Procurement contract No.KUP/M-146-2 of 2019-05-27 was signed with UAB "Music_LT", cost of the contract 6 999,98 EUR including VAT (5 529,98 EUR excluding VAT). Relates to: budget item 4.5, activity 3.3, Procurement plan point 37. | The procurement of 1 set of sound equipment by Beneficiary 3, date of launch: 2019-05-10 Type of procedure: single tender.
Contract for works No.CTP-25 of 2019-08-16 was signed with KUP "OrshaStroyTrest", cost of the contract 12641,72 EUR (exempt from taxes and VAT). Relates to: budget item 4.2, activity 3.4, Procurement plan point 39. | The procurement of renovation works for 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha, by Beneficiary 2, date of launch: 2019-07-15. Type of procedure: competitive negotiated procedure without publication.
For Lot No.1: Procurement Contract with "Good furniture" Ltd., Nr. MTP 2/23-12T of 2019-08-01, the cost of the contract is 4020 EUR (exempt from taxes and VAT). For Lot No.2: Procurement Contract with "Bona Arte" Ltd., Nr. MTP 2/24-12T of 2019-08-05, the cost of the contract is 4710 EUR (exempt from taxes and VAT). Both contracts relate to: budget item 4.6, activity 3.5, Procurement plan point 45. | The procurement of furniture by the Beneficiary 2, date of launch: 2019-07-04 Type of procedure: Competitive negotiated procedure without publication, as well as division of the subject of the procurement into two lots. A more competitive procedure than the one planned in the Procurement plan was used in order to intensify competition and to receive more competitive proposals. a) In lot No.1 there were announced 13 tables 1x2m, 70 chairs, 7 sofas. b) In lot No.2 there were announced 7 decorative screens for heating elements, 27 lamps styled/decorated according to the ancient pattern.
In case of complex procurements, or deviations from the Procurement plan, in order to avoid unclarity and additional questions it is recommended to explain to which budget item, activity, point of the procurement plan the awarded contracts relate.
It is possible to apply more competitive procedure from Annex II than the one planned in the Procurement plan.
It is allowed to divide the procurement into lots, however on condition that they will be procured using the procedure applicable for the whole unsplit amount (no artificial lowering of the procedure is allowed).
In this case each lot shall be described separately, including which items were purchased within which lot.
If the procedure differs from the one indicated in the Procurement plan (or is implemented differently) please provide explanation and justification on how it corresponds to the national legal acts (for LV, LT Beneficiaries) or to ANNEX II to the Guidelines for Applicants (for BY Beneficiaries).
Be specific and laconic, provide main facts: when procedure was launched, type of procedure. There is no need to include information about unsuccessful procedures.
Even if costs are not reported in the currect reporting period (e.g., audit), still the contract and the respective procedure shall be described (e.g., the contract was concluded, but no invoices were received yet).
Also, if you have started a procedure during the reporting period, but due to complains or other reasons the procedure was not finalised yet, please provide this information. Provision of this information shall be also ensured in the progress report for the period when the procedure was finalised.
Provide information about each concluded contract above 3000 EUR without VAT. List the name of the winner, title of the contract and amount.

## Financial Report
5. PROGRESS FINANCIAL REPORT | [15 empty] | B2 | B3
EXPENDITURE | Lead Beneficiary / No of Beneficiary | Original budget |  |  |  | Allowed reallocations | Expenditures incurred in reporting period |  |  | Accumulated expenditures in previous reporting periods (in EUR)* | Balance (from project start including current report), in EUR | Next reporting period |  |  | Balance (from project start including current report and forecast), in EUR
|  | Unit | No of units | Unit rate (in EUR) | Costs (in EUR) |  | No of units | Unit rate (in EUR) | Costs (in EUR) |  |  | No of units | Unit rate (in EUR) | Costs (in EUR)
1. Human Resources
1.1. Project manager, LV | Lead Beneficiary | Per hour | 1820 | 18.04 | 32832.8 |  | 423 | 17.7358 | 7502.26 | 1313.86 | 24016.68 | 423 | 18.04 | 7630.92 | 16385.76
1.2. Financial manager, LV | Lead Beneficiary | Per hour | 700 | 10.68 | 7476 |  | 155 | 10.673 | 1654.32 | 1090.2 | 4731.48 | 155 | 10.68 | 1655.4 | 3076.08
1.3. Public procurement specialist | Lead Beneficiary | Per hour | 1110 | 10.61 | 11777.1 |  | 423 | 9.6044 | 4062.67 | 627.52 | 7086.91 | 423 | 10.61 | 4488.03 | 2598.88
1.4. Construction expert | Lead Beneficiary | Per month | 1.2 | 1165.1 | 1398.12 |  | 0.6 | 1034.9833 | 620.99 | 578.17 | 198.96 | 0.6 | 331.6 | 198.96 | 0
1.5. Local coordinator, part time (50 %), BY | Beneficiary No 2 | Per month | 12 | 490 | 5880 |  | 3 | 484.168 | 1452.5 | 1035.42 | 3392.08 | 3 | 490 | 1470 | 1922.08
1.6. Local accountant, part time (50 %), BY | Beneficiary No 2 | Per month | 12 | 380 | 4560 |  | 3 | 378.685 | 1136.06 | 701.71 | 2722.23 | 3 | 380 | 1140 | 1582.23
1.7. Local coordinator, LT | Beneficiary No 3 | Per day | 150 | 75 | 11250 |  | 40 | 70.9435 | 2837.74 | 4543 | 3869.26 | 40 | 75 | 3000 | 869.26
1.8. Local accountant, LT | Beneficiary No 3 | Per day | 150 | 69 | 10350 |  | 40 | 66.9785 | 2679.14 | 3730.43 | 3940.43 | 40 | 69 | 2760 | 1180.43
Subtotal Human Resources |  |  |  |  | 85524.02 |  |  |  | 21945.68 | 13620.31 | 49958.03 |  |  | 22343.31 | 27614.72
2. Travel and accommodation
2.1. Travel of project staff to events in Orsha, Belarus (PMG meeting, conference, 2 seminars, joint exhibition) | Beneficiary No 3 | Per project | 1 | 1200 | 1200 |  |  |  | 0 |  | 1200 | 1 | 800 | 800 | 400
2.2. Travel of project the events in Orsha, Belarus (PMG meeting, conference, 2 seminars, joint exhibition) | Lead Beneficiary | Per project | 1 | 750 | 750 |  |  |  | 0 |  | 750 |  |  | 0 | 750
2.3. Rent of transport to project events | Beneficiary No 3 | Per project | 1 | 1750 | 1750 |  | 1 | 218.3 | 218.3 |  | 1531.7 |  |  | 0 | 1531.7
2.4. Rent of transport to project events | Lead Beneficiary | Per project | 1 | 2590 | 2590 |  | 1 | 927 | 927 |  | 1663 |  |  | 0 | 1663
2.5. Accommodation of participants of Medival festival | Beneficiary No 3 | Per person/day | 40 | 35 | 1400 |  |  |  | 0 |  | 1400 |  |  | 0 | 1400
2.6. BY visas and insurances for staff | Lead Beneficiary | Per project | 1 | 616 | 616 |  | 1 | 150 | 150 |  | 466 | 1 | 100 | 100 | 366
2.7. LV visas and insurances for staff | Beneficiary No 2 | Per project | 1 | 493 | 493 |  | 1 | 120 | 120 |  | 373 | 1 | 100 | 100 | 273
2.8. Travel of partners to working group meetings | Beneficiary No 2 | Per trip | 5 | 128 | 640 |  |  |  | 0 | 88 | 552 | 1 | 28 | 28 | 524
2.9. Travel to 2 Programme events | Beneficiary No 2 | Per project | 1 | 300 | 300 |  |  |  | 0 |  | 300 | 1 | 150 | 150 | 150
2.10. Travel to 2 Programme events | Lead Beneficiary | Per project | 1 | 150 | 150 |  |  |  | 0 |  | 150 | 1 | 75 | 75 | 75
2.11. Travel to 2 Programme events | Beneficiary No 3 | Per project | 1 | 200 | 200 |  |  |  | 0 |  | 200 | 1 | 100 | 100 | 100
Subtotal Travel and accommodation |  |  |  |  | 10089 |  |  |  | 1415.3 | 88 | 8585.7 |  |  | 1353 | 7232.7
3. Supplies, external services and other costs
3.1. Expenditure verification (audit) | Beneficiary No 2 | Per service | 1 | 3500 | 3500 |  | 1 | 500 | 500 |  | 3000 | 1 | 100 | 100 | 2900
3.2. Expenditure verification (audit) | Beneficiary No 3 | Per service | 1 | 1000 | 1000 |  | 1 | 200 | 200 |  | 800 | 1 | 150 | 150 | 650
3.3. Articles about the project in the press | Lead Beneficiary | Per item | 2 | 250 | 500 |  |  |  | 0 |  | 500 | 1 | 200 | 200 | 300
3.4. Articles about the project in the press | Beneficiary No 2 | Per item | 2 | 150 | 300 |  | 1 | 145 | 145 |  | 155 |  |  | 0 | 155
3.5. Publication costs (5 articles) | Beneficiary No 3 | Per item | 5 | 100 | 500 |  | 1 | 117.32 | 117.32 | 91.89 | 290.79 | 1 | 100 | 100 | 190.79
3.6. Tourism promotion event "Life of Medieval Manor" (catering, rent of equipment, event materials - 150 leaflets, 4 posters) | Beneficiary No 3 | Per event | 1 | 5200 | 5200 |  | 1 | 4979.83 | 4979.83 |  | 220.17 |  |  | 0 | 220.17
3.7. Joint exhibition of local craftsmen and artists (catering 34 persons, supplies for arts and crafts) | Beneficiary No 2 | Per event | 1 | 2375 | 2375 |  | 1 | 2369 | 2369 |  | 6 |  |  | 0 | 6
3.8. Organisation of the conference in Vitebsk (catering, rent of equipment, conference and promotion materials) | Beneficiary No 2 | Per event | 1 | 4938 | 4938 |  |  |  | 0 |  | 4938 | 1 | 2920 | 2920 | 2018
3.9. Set of printed products for the joint exhibition | Beneficiary No 2 | Per service | 1 | 800 | 800 |  |  |  | 0 |  | 800 | 1 | 800 | 800 | 0
3.10. Promotional items: 110 notebooks with visibility elements | Beneficiary No 2 | Per project | 1 | 1700 | 1700 |  |  |  | 0 | 898.59 | 801.41 | 1 | 800 | 800 | 1.41
3.11. Catering for 3 trainings for specialists | Lead Beneficiary | Per project | 1 | 1155 | 1155 |  |  |  | 0 |  | 1155 | 1 | 1155 | 1155 | 0
3.12. Lecturing service for 3 trainings for the specialists | Lead Beneficiary | Per project | 1 | 1700 | 1700 |  |  |  | 0 |  | 1700 | 1 | 1700 | 1700 | 0
3.13. Banking services | Lead Beneficiary | Per project | 1 | 200 | 200 |  | 1 | 50 | 50 | 100 | 50 | 1 | 50 | 50 | 0
3.14. permanent plaque (1) | Lead Beneficiary | Per project | 1 | 605 | 605 |  |  |  | 0 |  | 605 | 1 | 305 | 305 | 300
3.15. Set of stickers | Beneficiary No 2 | Per set | 1 | 106 | 106 |  | 1 | 86 | 86 |  | 20 |  |  | 0 | 20
3.16. Promotional video (3 minutes) | Beneficiary No 2 | Per item | 1 | 1100 | 1100 |  |  |  | 0 |  | 1100 |  |  | 0 | 1100
3.17. Supervision of construction works | Lead Beneficiary | Per service | 1 | 3000 | 3000 |  |  |  | 0 |  | 3000 | 1 | 3000 | 3000 | 0
3.18. Author supervision | Lead Beneficiary | Per service | 1 | 2500 | 2500 |  |  |  | 0 |  | 2500 | 1 | 2500 | 2500 | 0
Subtotal Supplies, external services and other costs |  |  |  |  | 31179 |  |  |  | 8447.15 | 1090.48 | 21641.37 |  |  | 13780 | 7861.37
4. Works and long-term investments
4.1. Renovation of exhibition hall, Uzvaras Str. 17, Daugavpils (111,13 m²) GA 3.1 | Lead Beneficiary | Per project | 1 | 73780 | 73780 |  | 1 | 33680.81 | 33680.81 |  | 40099.19 | 1 | 40000 | 40000 | 99.19
4.2. Renovation of 2 exhibition halls and service rooms (45 m2), Kalvarijskaja 83, Orsha | Beneficiary No 2 | Per project | 1 | 17300 | 17300 |  | 1 | 4641.72 | 4641.72 |  | 12658.28 | 1 | 8000 | 8000 | 4658.28
4.3. Construction open-air stage (315 m2), Kupiskis, LT. | Beneficiary No 3 | Per project | 1 | 88871.3 | 88871.3 |  |  |  | 0 |  | 88871.3 | 1 | 45000 | 45000 | 43871.3
4.4. Lighting equipment (10 scenic floodlights) | Beneficiary No 3 | Per set | 1 | 2500 | 2500 |  |  |  | 0 |  | 2500 | 1 | 2500 | 2500 | 0
4.5. Sound equipment | Beneficiary No 3 | Per set | 1 | 11000 | 11000 |  | 1 | 6999.98 | 6999.98 |  | 4000.02 |  |  | 0 | 4000.02
4.6. Furniture for exhibition halls in Orsha (including 13 tables 1x2m, 70 chairs, 7 sofas, 27 lamps, 7 decorative screens for heating elements) | Beneficiary No 2 | Per project | 1 | 8870 | 8870 |  | 1 | 8730 | 8730 |  | 140 |  |  | 0 | 140
4.7. 1 stationary demonstration screen, 1 stationary projector, 1 tablet computer | Beneficiary No 3 | Per project | 1 | 2300 | 2300 |  |  |  | 0 |  | 2300 | 1 | 2300 | 2300 | 0
4.8. Multimedia projector | Beneficiary No 2 | Per item | 1 | 1500 | 1500 |  |  |  | 0 | 1432.7 | 67.3 |  |  | 0 | 67.3
Subtotal Works and long-term investments |  |  |  |  | 206121.3 |  |  |  | 54052.51 | 1432.7 | 150636.09 |  |  | 97800 | 52836.09
5. Preparation costs
5.1. Preparation of technical studies and documentation (up to 5% of the cost of the infrastructure component financed by the Programme within the project to which these documents were required) | Beneficiary No 3 |  | 1 | 3200 | 3200 |  |  |  | 0 | 3200 | 0 |  |  | 0 | 0
Subtotal Preparation costs |  |  |  |  | 0 |  |  |  | 0 | 3200 | 0 |  |  | 0 | 0
6. Subtotal direct eligible costs of the project (1-5) |  |  |  |  | 336113.32 |  |  |  | 85860.64 | 19431.49 | 230821.19 |  |  | 135276.31 | 95544.88
7. Indirect administrative costs (maximum 7% of BH 1 "Human Resources".) | All beneficiaries |  |  |  | 5986.6814 |  |  |  | 1536.1976 | 831.82 | 3618.6638 |  |  | 1564.0317 | 2054.6321
8. Total eligible costs (6+7) |  |  |  |  | 342100.0014 |  |  |  | 87396.8376 | 20263.31 | 234439.8538 |  |  | 136840.3417 | 97599.5121
* In case of the first Progress Report this column shall not be filled.
Lead Beneficiary/Beneficiary No:
|  | <insert name of organisation, position, name and surname of the chief accountant> | [5 empty] | <insert date of signature of the Report> |  | <signature>
Shall be signed, dated by the chief accountant.
Hours reported (time devoted to work on project) should match with the timesheets filled in and provided to the auditors, project budget and internal documents of allocation of staff to the project at Beneficiary's organisation!
Budget with all requested and approved minor amendments, if there were such, shall be reflected.
(If there were substantial amendments to the project budget approved and came into force, changed budget after substantial amendments shall be reflected.)
Recommended to report expenditures only 2 digits after comma! Verify proper rounding in the tables.
Reported unit rate can be different from the planned in the project budget.
Amount should match total expenditures incurred during the previous reporting period(s) in other budget tables!
Real costs incurred and paid in reporting period should be indicated.
Realistic forecast of costs for the next reporting period shall be done.
Formulas must be respected throughout the document.
Verify the calculations, formulas in each line; the amounts must coincide.
Amount should match total expenditures in other budget/report tables (Section 6, Section 7)! Verify, if amounts were calculated correctly!
For all the tables and all costs and Budget Headings: verify, if amounts were calculated correctly!
Preparation costs, if there were such, shall be reported with the first Progress report!

## Financial Summary
6. FINANCIAL SUMMARY BY EACH BENEFICIARY AND BUDGET HEADING
Contracted budget by beneficiaries
Beneficiary Budget heading | Lead Beneficiary | Beneficiary No.2 | Beneficiary No.3 | Beneficiary No.4 | Beneficiary No.5 | Beneficiary No.6 | Beneficiary No.7 | Beneficiary No.8 | Total
Region (core, adjoining region) | core region | core region | core region | [6 empty] | core region | adjoining region
1. Human resources | 53484.02 | 10440 | 21600 | [5 empty] | 85524.02
2. Travel and accommodation | 4106 | 1433 | 4550 | [5 empty] | 10089
3. Supplies, external services and other costs | 9660 | 14819 | 6700 | [5 empty] | 31179
4. Works and long-term investments | 73780 | 27670 | 104671.3 | [5 empty] | 206121.3
5. Preparation costs |  |  | 3200 | [5 empty] | 3200
6. Total direct eligible costs of the project (1+5) | 141030.02 | 54362 | 140721.3 | [5 empty] | 336113.32
7. Indirect administrative costs | 3743.8814 | 730.8 | 1512 | [5 empty] | 5986.6814
Total eligible costs (6+7) | 144773.9014 | 55092.8 | 142233.3 | 0 | 0 | 0 | 0 | 0 | 342100.0014
Expenditures incurred during previous reporting period (-s)*
1. Human resources | 3609.75 | 1737.13 | 8273.43 | [5 empty] | 13620.31
2. Travel and accommodation |  | 88 | [6 empty] | 88
3. Supplies, external services and other costs | 100 | 898.59 | 91.89 | [5 empty] | 1090.48
4. Works and long-term investments |  | 1432.7 | [6 empty] | 1432.7
5. Preparation costs |  |  | 3200 | [5 empty] | 3200
6. Total direct eligible costs of the project (1+5) | 3709.75 | 4156.42 | 11565.32 | [5 empty] | 19431.49
7. Indirect administrative costs | 252.6825 | 121.5991 | 457.54 | [5 empty] | 831.8216
Total eligible costs (6+7) | 3962.4325 | 4278.0191 | 12022.86 | 0 | 0 | 0 |  | 0 | 20263.3116
Expenditures incurred during reporting period
1. Human resources | 13840.24 | 2588.56 | 5516.88 | [5 empty] | 21945.68
2. Travel and accommodation | 1077 | 120 | 218.3 | [5 empty] | 1415.3
3. Supplies, external services and other costs | 50 | 3100 | 5297.15 | [5 empty] | 8447.15
4. Works and long-term investments | 33680.81 | 13371.72 | 6999.98 | [5 empty] | 54052.51
5. Preparation costs | [8 empty] | 0
6. Total direct eligible costs of the project (1+5) | 48648.05 | 19180.28 | 18032.31 | [5 empty] | 85860.64
7. Indirect administrative costs | 968.8168 | 181.1992 | 386.1816 | [5 empty] | 1536.1976
Total eligible costs (6+7) | 49616.8668 | 19361.4792 | 18418.4916 | 0 | 0 | 0 | 0 | 0 | 87396.8376
Balance after reporting period
1. Human resources | 36034.03 | 6114.31 | 7809.69 | [5 empty] | 49958.03
2. Travel and accommodation | 3029 | 1225 | 4331.7 | [5 empty] | 8585.7
3. Supplies, external services and other costs | 9510 | 10820.41 | 1310.96 | [5 empty] | 21641.37
4. Works and long-term investments | 40099.19 | 12865.58 | 97671.32 | [5 empty] | 150636.09
5. Preparation costs | [8 empty] | 0
6. Total direct eligible costs of the project (1+5) | 88672.22 | 31025.3 | 111123.67 | [5 empty] | 230821.19
7. Indirect administrative costs | 2522.3821 | 428.0017 | 668.2784 | [5 empty] | 3618.6622
Total eligible costs (6+7) | 91194.6021 | 31453.3017 | 111791.9484 | 0 | 0 | 0 | 0 | 0 | 234439.8522
Modifications to the Project budget between beneficiaries
To be filled-in in the event modifications to the budget were related to reallocations between beneficiaries' budgets.
* In the first Progress Report this part of table shall not be filled in and therefore can be deleted.
Lead Beneficiary/Beneficiary No:
<insert name of organisation, position, name and surname of the chief accountant> |  |  | <insert date of signature of the Report> |  | <signature>
Budget with all requested and approved minor amendments, if there were such, shall be reflected.
(If there were substantial amendments to the project budget approved and came into force, changed budget after substantial amendments shall be reflected.)
For the second and/or subsequent reports: expenditures incurred during previous reporting period(s) shall be indicated.
Expenditures incurred during current reporting period shall be indicated.
To be filled in if there were modifications to the project budget between beneficiaries.
Select from the drop list the beneficiary's region: core or adjoining
Shall be signed, dated by the chief accountant.
Amount should match total expenditures in other budget tables.
Amount should match total expenditures incurred during previous reporting period(s) in other budget tables.

## Sources of F
7. SOURCES OF FUNDING
Source of Funding | Planned / contracted (in EUR) | Reported (in EUR) | Percentage (%) | Accumulated co-financing in previous reporting period(s) (in EUR)* | Percentage (%) | Forecast for next reporting period (in EUR)
EU FUNDING (GRANT AMOUNT) | 307890 | 78657.16 | 90% | 18185.78 | 89.75% | 133840.34
TOTAL CO-FINANCING BY THE BENEFICIARIES | 34210 | 8739.6838 | 10% | 2077.53 | 10.25% | 3000
Co-financing by Lead Beneficiary: | 12009.2 | 4961.6867 | 5.677% | 386.24 | 1.906% | 1000
state budget | 6004.6 |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget | 6004.6 | 4961.6867 | 5.677% | 386.24 | 1.906% | 1000
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 2 | 10400.45 | 1936.1479 | 2.215% | 806.03 | 3.978% | 1000
state budget |  |  | 0% |  | 0%
regional authority budget | 10400.45 | 1936.1479 | 2.215% | 806.03 | 3.978% | 1000
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 3 | 11800.35 | 1841.8492 | 2.107% | 885.26 | 4.369% | 1000
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget | 11800.35 | 1841.8492 | 2.107% | 885.26 | 4.369% | 1000
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 4 | 0 | 0 | 0% | 0 | 0% | 0
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 5 | 0 | 0 | 0% | 0 | 0% | 0
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 6 | 0 | 0 | 0% | 0 | 0% | 0
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 7 | 0 | 0 | 0% | 0 | 0% | 0
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
Co-financing by Beneficiary 8 | 0 | 0 | 0% | 0 | 0% | 0
state budget |  |  | 0% |  | 0%
regional authority budget |  |  | 0% |  | 0%
municipal budget |  |  | 0% |  | 0%
other (specify) |  |  | 0% |  | 0%
TOTAL PROJECT FUNDING | 342100 | 87396.8438 | 100% | 20263.31 | 100% | 136840.34
* In case of the first Progress Report this column shall not be filled.
Lead Beneficiary:
Administration of Druskininkai Municipality, Head of Finance and Accountancy Division, Julija Ramanauskienė | 2020-01-24
Total co-financing of the set percentage shall be reached by the end of the project, thus in the progress report the cumulative amount of the co-financing from the previous reports can be different (not necessarily 10%).
Initial project budget shall be indicated
(Section 11, Budget table 2 in the Project Description).
Reported grant amount of the reporting period to be indicated.
Total amount to be verified with other tables of the Report.
Co-financing of the reporting period to be indicated by each Beneficiary.
The % of the co-financing can differ in each reporting period, but should be as contracted at the end of the project.
Percentage of the co-financing of each beneficiary from the reported costs can be different in each reporting period. Reporting of the set percentage of the cofinancing from the reported costs in each progress report is not mandatory.
Cumulative information from the previous reports (both grant amount and co-financing of beneficiaries) to be transferred and verified with other tables in the current and previous reports!
Total amount to be verified with the Table 5 of the Report.

## Payment Details
8. DETAILED REPORT OF EXPENDITURE FOR EACH BUDGET ITEM AND BENEFICIARY
No | No of the budget item | Name of the product / service / work element/ expenditure | Document No | Date when the document was issued | Name of the supplier/service provider | Registration/ identity No of the supplier / organisation | Date when the document was paid | Form of payment: (R-Remittance) (C-Cash) | Total eligible amount in national currency | Exchange rate** | Total eligible amount in EUR | Lead Beneficiary / Beneficiaries
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | 1.1. | Name Surname , Project manager LV, part-time (20%), gross, GA 1.1, GA 1.2 | Pay slip No. 7 | 2019-04-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-04-30 | R | 280.08 | 1 | 280.08 | LB | 1546.74
2 |  |  | Pay slip No. 8 | 2019-05-31 | Administration of XXXXX Municipality | XXXXXXXX | 2019-05-31 | R | 280.08 | 1 | 280.08 | LB | 1149.23
3 |  |  | Pay slip No. 9 | 2019-06-28 | Administration of XXXXX Municipality | XXXXXXXX | 2019-06-28 | R | 117.93 | 1 | 117.93 | LB | 0
4 |  |  | Pay slip No. 10 | 2019-07-31 | Administration of XXXXX Municipality | XXXXXXXX | 2019-07-31 | R | 289.69 | 1 | 289.69 | LB | #REF!
5 |  |  | Pay slip No. 11 | 2019-08-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-08-30 | R | 270.06 | 1 | 270.06 | LB | #REF!
6 |  |  | Pay slip No. 12 | 2019-09-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-09-30 | R | 308.9 | 1 | 308.9 | LB | #REF!
7 | 1.2. | Name Surname LV , Financial manager, part time (20%), gross, GA 1.1, GA 1.2 | Pay slip No. 7 | 2019-04-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-04-30 | R | 205.52 | 1 | 205.52 | LB
8 |  |  | Pay slip No. 8 | 2019-05-31 | Administration of XXXXX Municipality | XXXXXXXX | 2019-05-31 | R | 205.52 | 1 | 205.52 | LB
9 |  |  | Pay slip No. 9 | 2019-06-28 | Administration of XXXXX Municipality | XXXXXXXX | 2019-06-28 | R | 121.63 | 1 | 121.63 | LB
10 |  |  | Pay slip No. 10 | 2019-07-31 | Administration of XXXXX Municipality | XXXXXXXX | 2019-07-31 | R | 205.52 | 1 | 205.52 | LB
11 |  |  | Pay slip No. 11 | 2019-08-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-08-30 | R | 205.52 | 1 | 205.52 | LB
12 |  |  | Pay slip No. 12 | 2019-09-30 | Administration of XXXXX Municipality | XXXXXXXX | 2019-09-30 | R | 205.52 | 1 | 205.52 | LB
13 | 1.3. | [10 empty] | LB
14 | 1.4. | [10 empty] | LB
21 | 1.5. | Name Surname, Local coordinator BY, Name Surname part time (50 %), gross, GA 1.1, GA 1.2 | Salary record sheet No 3 for March, 2019 | 2019-03-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-04-03 | C | 502.4 | 0.4122 | 207.08 | B2
22 |  |  | Salary record sheet No 4 for April, 2019 | 2019-04-30 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-05-14 | C | 495.03 | 0.41834 | 207.09 | B2
23 |  |  | Salary record sheet No 5 for May, 2019 | 2019-05-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-06-06 | C | 486.93 | 0.42526 | 207.07 | B2
24 |  |  | Salary record sheet No 6 for June, 2019 | 2019-06-30 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-07-16 | C | 481.82 | 0.42981 | 207.09 | B2
25 |  |  | Salary record sheet No 7 for July, 2019 | 2019-07-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-08-16 | С | 479.81 | 0.43161 | 207.09 | B2
|  |  | Salary record sheet No 8 for August, 2019 | 2019-08-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-09-09 | C | 468.37 | 0.44215 | 207.08 | B2
| 1.6. | Name Surname BY , Financial manager, part time (20%), gross, GA 1.1, GA 1.2 | Salary record sheet No 3 for March, 2019 | 2019-03-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 03.04.2019 | C | 340.49 | 0.4122 | 140.34 | B2
|  |  | Salary record sheet No 4 for April, 2019 | 2019-04-30 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-05-14 | C | 335.5 | 0.41834 | 140.35 | B2
|  |  | Salary record sheet No 5 for May, 2019 | 2019-05-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-06-06 | C | 330 | 0.42526 | 140.33 | B2
|  |  | Salary record sheet No 6 for June, 2019 | 2019-06-30 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-07-16 | C | 326.54 | 0.42981 | 140.35 | B2
26 |  |  | Salary record sheet No 7 for July, 2019 | 2019-07-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-08-16 |  | 325.18 | 0.43161 | 140.35 | B2
|  |  | Salary record sheet No 8 for August, 2019 | 2019-08-31 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-09-09 | C | 317.42 | 0.44215 | 140.34 | B2
| 1.7 | Name Surname, Local coordinator, part time (50 %) | PR7 | 2019-04-30 | XXXXX town municipality | XXXXXXXX | 2019-04-30, 2019-05-03 | R | 800 | 1 | 800 | B3
| 1.8 | Name Surname, Local accountant, part time (50 %) | PR7 | 2019-04-30 | XXXXX town municipality | 188211432 | 2019-04-30, 2019-05-03 | R | 433.33 | 1 | 433.33 | B3
| 2.3 | 2.3. Travel of project event participants to Seminar from XX town to XX town 2019-05-27/28 (1 two-way travel: Vehicle rent (1 day seminar/10 persons) GA 4.3.2, Annex No XX | Invoice Nr.1310 | 2019-06-28 | LTD "Bus rent" | XXXXXXXX | 2019-07-11 | R | 218.3 | 1 | 218.3 | B3
| 2.22 | Daily allowances for meetings of the working group and partners Activity 1.1 (Name Surname) | Report of the travel No xxx, Order of the Director of the organisation No 9-k | 2019-09-30 | XXXXXXXXXXXX Region Executive Committee | XXXXXXXX | 2019-09-30 | С | 68 | 0.43699 | 29.71 | B2
27 | 3.5. | Expenditure verification (audit) GA 1.2 | Invoice AC Nr.190505 | 2019-05-07 | LTD " AUDIT" | XXXXXXXX | 2019-05-07 | R | 152.97 | 1 | 152.97 | B3
28 | [8 empty] | 9258.06 |  | 6414.84
36 |  | Lead Beneficiary:
37 |  | Head of Finance and Accountancy Division, XXXXXXXXXX |  |  |  |  | DATE
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
* Add as much rows as you need. Please, respect formulas in the column No 12.
** Follow the guiding of use of exchange rate
Please sort the documents by the order of the budget items indicated in the Table 5 and by beneficiaries. Different budget items and Beneficiaries shouldn'd be mixed.
Please follow the order: enter the information according to the reported budget lines (Table 5).
For the Budget Heading 1, enter the title and the registration No of the Beneficiary's organisation.
Please check all total amounts with the information indicated in the reported budget items of the Table 5.
It is preferable to indicate not only the No of the document, but the title of it as well.
It is preferable to indicate the number of activity (e.g., Activity 2.3) the costs reported are related to.
Information of the service provider to be entered.
Remember to verify the total amount with the amount in other tables of the Report.
Important: entering the information about the documents for the Budget Heading 7 and for the Budget Heading 5 (except for preparation of the technical documentation), is not required.
To be signed by the chief accountant of the organisation.
Currency shall be converted into Euro using the monthly accounting exchange rate of the EC (InforEuro) in the month during which that expenditure was incurred (invoiced).
Monthly exchange rate (InforEuro) with an accuracy of 4 digits after comma. Rounding shall be made according to the mathematical rounding rule.
It is preferable to indicate the No of th Annex to the Report where the participants of the event are listed.
Otherwise the participants shall be mentioned in the table.
Information regarding paid salary has to be provided for each month.
Please verify if dates of issued documents and payments made are in line with the reporting period.
Please ensure that the number of budget item is indicated correctly and is related to the description of the costs.

## Outside Area
9. EXPENDITURE OUTSIDE THE PROGRAMME AREA
Activities | Beneficiary (number) | Contracted budget outside the Programme area (in EUR) | Expenditure outside the Programme area in the reporting period (in EUR) | Accumulated expenditure outside the Programme area in the previuos reporting period(s) (in EUR)
Activity X.X. "Work in the archives in Warsaw, Poland" | 0 | 3000 | 1000 | 2000
Activity (specify) | 0 | 0 | 0 | 0
Activity (specify) | 0 | 0 | 0 | 0
Activity (specify) | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Total |  | 3000 | 1000 | 2000
Lead Beneficiary:
Head of Finance and Accountancy Division, XXXXXXXXXXXX |  |  | DATE
Please follow total amount indicated in the Table 12 of the contracted project description.
Total amount can be calculated summing up different costs (budget items) of the same activity. In presented case it could be per-diems, travel tickets, accommodation costs. ect.
Information shall mach the reported costs indicated in the Table 5 of the Report.
Remember to indicate the accumulated amount(s) from the previous Report(s)
To be signed even if such costs are not planned in the budget or not reported in the current Progress Report.
To be signed by the chief accountant of the organisation.

## Annexes
10. ANNEXES
1. Add as many rows as necessary and delete information/rows which are not applicable.
2. Indicate annexes which prove the implemented activities and achieved outputs. Sort the very annexes accordingly as supporting documents attached to the report. The annexes to be attached must correspond with the table of supporting documents of the Guidelines for Applicants and Beneficiaries. Mark a box with T if an original and/or a copy(ies) are attached to the report.
The list of the attached annexes to the Report: |  | Original | Copy(ies)
1. Documents related to the GA1
1) Annex No.1: LB order No. SR-23 of 2019-04-06 regarding staff appointment to the project. |  |  | X
2) Annex No.2: B2 order No.B-457 of 2019-04-13 regarding staff appointment to the project. |  |  | X
3) Annex No.3: B3 order No. D46/345 of 2019-04-22 regarding local coordinator and local accountant allocation to the project. |  |  | X
4) Annex No.3A: LB order No. SR-31 of 2019-04-24 regarding formation and functions of the PMG. |  |  | X
5) Annex No.4: LB order No. SR-21 of 2019-04-04 regarding staff appointment to PSG. |  |  | X
6) Annex No.5: B2 order No. B-456 of 2019-04-12 regarding staff appointment to PSG. |  |  | X
7) Annex No.6: B3 order No.D45/345 of 2019-04-21 regarding staff appointment to PSG. |  |  | X
8) Annex No.7: Photos, List of participants, Agenda and Minutes of the PMG meeting on 15 May 2019 in Daugavpils |  |  | X
9) Annex No.8: Photos, List of participants, Agenda and Minutes of the PMG meeting on 08 August 2019 in Orsha. |  |  | X
2. Documents related to the GA2
1) Annex No.9: copy of the article "The neighbours share common interests" by B2 |  |  | X
2) Annex No.10: copy of the article "Bendradarbiavimas per sieną - renginys Kupiškio Dvare" by B3 |  |  | X
3) Annex No.11: print-out of the news update "Pošvaļdeibys puorstuovji pīsadola projekta „Myusu viesturiskais montuojums“ atkluošonys pasuokumā Oršā, Boltkrīvejā" on the LB web-site, with analytics |  |  | X
4) Annex No.12: print-out of the news update "Kupiškis pradėda naują projektą" on the B3 web-site, with analytics |  |  | X
5) Annex No.13: print-out of the publication in B2 social network (Facebook) account „Opening of the Joint Exhibition“, with analytics |  |  | X
6) Annex No.14: print-out of the publication in B2 social network (Facebook) account „Closing of the joint exhibition – new impressions“, with analytics |  |  | X
7) Annex No.15: photo of the temporary billboard for works by LB. |  |  | X
8) Annex No.16: photo of the temporary billboard for works by B2. |  |  | X
9) Annex No.17: photo of set of Stickers for labelling of equipment (20) by B3 |  |  | X
10) Annex No.18: photo of set of Stickers for labelling of equipment (125) by B2 |  |  | X
11) Annex No.19: print-out (e-version) of the newsletter for specialists in culture and tourism in three languages, with a screenshot proving its sending to the specialists. |  |  | X
12) Annex No.20: photos of 3 Project posters placed in each Beneficiary's premises |  |  | X
3. Documents related to the GA3
1) Annex No.21: Photos of the progress of works by LB, renovation of exhibition hall in Daugavpils Culture House. |  |  | X
In case the works have been finalised and commissioned into exploitation: Annex No.21A Commissioning into Exploitation Act (if required by the national legislation). |  |  | X
2) Annex No.22: Photos of the set of sound equipment by B3, with visibility elements (stickers). |  |  | X
3) Annex No.23: Photos of the progress of works by B2, renovation of 2 exhibition halls and service rooms in Orsha Museum . |  |  | X
4) Annex No.24: Photos of the furniture by B2 with information plates in exhibition halls, where equipment located, with visibility elements (stickers). |  |  | X
4. Documents related to the GA 4
1) Annex No.25: Photos, List of participants, Agenda and Report of the tourism promotion event "Life of Medieval Manor", by B3. |  |  | X
2) Annex No.26: print-out from B3 Facebook account with the feedback of the tourism promotion event. |  |  | X
3) Annex No.27: summary of the survey of the participants of the tourism promotion event by B3. |  |  | X
4) Annex No.28: photos of the posters and leaflets to promote the event by B3. |  |  | X
5) Annex No.29: the agenda, list of participants, photos, report of the opening ceremony and first 2 days of the exhibition "Crafts through centuries" by B2. |  |  | X
6) Annex No.30: copies of the pages of the registration journal of the visitors of the exhibition "Crafts through centuries", by B2. |  |  | X
7) Annex No.31: photos of the procured supplies and materials for the exhibition "Crafts through centuries", by B2. |  |  | X
8) Annex No.32: photos of the printed products for the exhibition (poster, flyer, sticker, banner, roll-up) |  |  | X
9) Annex No.33: summary of evaluation, pages from the Book of visitors for the exhibition by B2. |  |  | X
5. Individual Expenditure Verification Reports
1) Individual Expenditure Verification Report of the Lead Beneficiary |  | X
2) Individual Expenditure Verification Report of the Beneficiary No 2 |  | X
3) Individual Expenditure Verification Report of the Beneficiary No 3 |  | X
6. Request for payment
1) Request for Payment of further pre-financing. |  | X
7. Economic Classification of the requested amount (for Lithuanian beneficiaries)
1) Economic Classification of the requested amount for B3 |  | X
8. Economic Classification of the expenditures (for Lithuanian beneficiaries)
1) Economic Classification of the expenditures for B3 |  | X
9. Proof of publication of the international tender (procurement notice) |  | n/a | n/a
10. Exploitation/commissioning acts or acceptance acts/certificates (for works) |  | n/a | n/a
11. Letters of endorsement
1) Endorsement letter by the B2. |  | X
2) Endorsement letter by the B3. |  | X
12. Document which proves the right/authorisation to sign the documents in case the head of organisation is substituted by an authorised representative
1) Authorisation (Power of attorney) authorising the Head of the Department of the Lead Beneficiary to sign the Report in the absence of the Head of Organisation. |  |  | X
The European Commission/ Managing Authority may wish to publicise the results of the project. Do you have any objection to this Progress Report being published on EuropeAid Co-operation Office/ Programme website? If so, please state your objections here:
I, the undersigned as the representative of the Lead Beneficiary, certify, that information submitted in this Progress Report and its annexes to our knowledge and conviction is true and corresponds to the project:
Name and position of the Signatory | Name, Surname, Director
Location | Daugavpils
Date | 2019-12-11
Signature
Please indicate and describe the Annexes properly. Ideally, it shall be clear that all the necessary annexes are attached at a glance.
Photos of the meetings shall demonstrate EU and Programme visibility elements.
For all publications in the Beneficiaries' web-sites and social networks, it is recommended to provide the analytics (number of views, reactions, likes, comments, etc.) in order to calculate how many of the target groups were informed.
In case some outputs were disseminated by email, please provide proof of sending.
If the equipment is rather specific and cannot be recognised by non-specialists, it is recommended to write which items are on the photo.
One or several Photos shall show all the purchased items, with visibility stickers (where possible), or under a visibility plate.
Where it is technically impossibe to provide the List of participants of the event/meeting with signatures for each day (e.g., due to a big number of participants) please provide an alternative proof of the number of visitors who participated.